ANNEX XV-AWG MEETING. SOUL, 28-29 MAY 2012

FOLLOW-UP ACTIONS LIST OF THE RECOMMENDATIONS OF AWG (updated 11 Nov 2012)

| Title of Recommendation | Text of Recommendation | Follow-up action | To be initiated by | Derivable | Target date | Status in July 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| Amendment of TC Statute (1) | Clarify whether submission to UN legal department is necessary, or if amendments could be effected by simply following Article 11 of the Statute | TCS would follow up with ESCAP and WMO on this matter | TCS ESCAP WMO | Information from ESCAP and WMO | Before November 2012 | As TC doesn’t belong to UN System, no need submit to UN legal Dep. |
| Invitation letters to the Governments for attending the annual sessions (2) | ESCAP to provide to TCS a list of addressees for of Governments of Members | ESCAP to send the list to TCS | ESCAP | List of addressees | 15 October 2012 | Done |
| Relevance of the text: “as part of the World Weather Watch Programme” in Terms of Reference of TC (3) | Clarify the relevance of the text: “as part of the World Weather Watch Prog.” towards the end of ToR of TC and to propose updated wording | TCS to remind WMO | TCS | Message from WMO to TCS updating the phrase | 15 October 2012 | In progress |
| To compile and consolidate a revised ToR of TCS for consideration at the Integrated Workshop (IWS) in Nanjing later this year (4) | Routine tasks originally under the ToR of TC Secretary should be integrated into the ToR of the TCS. | TC Secretaryto revise the TCS ToR for consideration at the 7thIntegrated Workshop (IWS) | TCS | Proposal of revised ToR of the TC Secretariat | 15 October 2012 | In progress |
| Review of ToR of AWG and WGs (5) | The ToRs should be separately reviewed by the respective groups, and any revisions or amendments to be made would be discussed and vetted at the 7thIWS. | Chairs of AWG, WGM, WGH. WGDRR, TRCG Will present proposed changes | Chairs of WGs | Proposals of revised ToR of the WGs | 15 October 2012 | In progress (requested by message dated 9/17/2012 4:39 PM and reminder on 11/08/2012) |
| Review the practice of appointing the outgoing of TC Chair as the new AWG Chair.The rationale of this approach should also be suitably reflected when reviewing and revising the ToR of AWG. (6) | It was agreed that Solution B in Annex X be adopted, such that AWG chairmanships could be de-linked from TC chairmanships and hence TC session hosting arrangement. | TCS will consult the Members on elective appointment of AWG Chair and Vice-chair for one year or more, duration of office | TCS/AWG | Summary of comments from the Members | 15 October 2012 | TCS requested opinions from the Members TCS/287-2012 – 8 Nov. 2012 |
| Decision and Action-based Documents and Consistent Follow-up of the Decisions and Recommendations (7) | Observations and comments made by KMA (Annex XI) were presented, and relevant suggestions would be taken into consideration in preparing future Annual Operating Plans (AOPs). | Mr CM Shun would provide some suggestions and samples of action-based documents for reference by TCS. | KMA/Mr CM Shun | Suggestions and samples of action-based documents | June - September | Mr. CM Shun delivered examples of follow-up documents used in ICAO (in June 2012) |
| Engagement of media representatives for discussion on CAP at the IWS. (8) | As CAP is related to message delivery at the users' end, it was considered a good opportunity to engage media representatives for more in-depth discussion at the IWS. | Mr Koji Kuroiwa would explore possibilities to engage media representatives at IWS after discussions with WMO/PWSP | Mr Koji Kuroiwa (WMO) | Participation of WMO/PWSP and media representatives in IWS |  | TCS requested organizers of IWS to invite represent. of media. WMO informed possib. of Google be represented |
| TCS was requested to call for earlier submission of country reports from Members.(9) | As country reports would be presented at the 7th IWS instead of TC 45th Session, TCS was requested to call for earlier submission of country reports from Members. | TCS to send letters inviting Members to send the reports earlier | TCS | Country reports delivered to TCS before the IWS | 15 November 2012 | TCS has requested Members (Letter TCS/193-2012-27 June). Several reminders were made |
| Usefulness and application of in-kind contributions (10) | TCS was requested to contact Members to provide information on their in-kind contributions. | TCS will request Members to provide information | TCS | Summary will be presented as inf. paper at the 45th Session. | 31 December 2012 | The Members were requested (TCS/248-2012- 15 October 2012) |
| Standardization and Harmonization of Members’ Practices (11) | Standardization and Harmonization of Members’ Practices to Promote Effective Warning, in particular Communication of Advisory and Warning Messages to the Users | Mr Lei Xiaotu indicated that WGM would consider this issue at the next IWS. | Chair of WGM |  |  | Reminder sent by TCS on 8 November, to Chair of WGM |
| Procedures for Hosting TCS and Selection of the Secretary for the next Four-Year Cycle (2015-2018) (12) | Procedures for Hosting TCS and Selection of the Secretary for the next Four-Year Cycle (2015-2018). TCS was tasked to request a document from the Macao SAR Government to confirm its intention. | Request Macao Government to express in writing the intention to host TCS in the period 2015-2018 | TCS | Letter from the Government of Macao | July 2012 | According to SMG, Macao is willing to host TCS for another 4 years, and a verbal consent was obtained from both the Secretary and the Office of the Commissioner of the Ministry of Foreign Affairs of China with Macao SAR |
| Transfer of TCS to another Member (13) | It was noted that the document “Criteria for Hosting the Typhoon Committee Secretariat” (Annex XIII XIV) could serve as guidelines for future reference. TCS was requested to formalize the procedures based on the existing practice. | Inform the Members on the “Criteria for Hosting the Typhoon Committee Secretariat” (Annex XIII XIV). | TCS | Circular Letter to Members inviting to submit candidatures to host TCS | September 2012 | TCS/268-2012, 26 October 2012. Only Malaysia replied up to now informing not be interested |
| Agreement between Nanjing University of Information Science and Technology(NUIST, Nanjing, China) and TC (14) | Mr. Edwin Lai undertook to provide some input to the draft agreement from TRCG perspectives, and subject to any revisions required | TCS to send draft provided by Mr. Kunitsugu, reviewed by Mr. Edwin Lai, to WMO RTC Nanjing | Mr. Edwin Lai/TCS | Agreement revised by WMO RTC | September/October | CMA informed that NUIST concurs with the reviewed version |
| Signing ceremony of the Agreement between NUIST, Nanjing and TC. (15) | As the next IWS would be held in NUIST, TCS was requested to consult NUIST on the possible arrangement of a signing ceremony. | TCS to request RTC information on signing ceremony | TCS | Information from RTC Nanjing | September/October | Signing to take place at the Opening Ceremony of IWS |
| Follow-up actions list regarding AWG meeting. Soul, 28-29 May 2012 (16) | TC Secretary was requested to draw up a follow-up actions list to remind the parties concerned and to aim at a timely completion of actions before the 7th IWS. | TCS will distribute a follow-up actions list of the recommendat. of AWG | TCS | Follow-up actions list | July | TCS sent the current document to the parties (WMO,ESCAP,AWG,members) |

# Footnotes

Considerations were given to the prevailing practice of appointing the outgoing TC Chairperson as the new AWG Chair (see Annex X for details). To address the issues arising, it was agreed that Solution B in Annex X be adopted, such that AWG chairmanships could be de-linked from TC chairmanships and hence TC session hosting arrangement.  Elective appointment of AWG Chair and Vice-chair for one year or more, duration of office to be further consulted among Members or as decided by TC at the annual sessions, would provide more continuity and enhance AWG's leadership role in planning and implementing TC's initiatives.