| ESCAP/WMO Typhoon Committee 16th Integrated Workshop 2 to 3 December 2021 Video Conference | FOR PARTICIPANTS ONLY 30 November 2021 ENGLISH ONLY |  |  | FOR PARTICIPANTS ONLY WRD/TC.53/8.1 20 January 2021 ENGLISH ONLY |
| --- | --- | --- | --- | --- |

DRAFT

SUMMARY REPORT on Activities of Working Group on Disaster Risk Reduction

(WGDRR) of TC in 2021

(Submitted by WGDRR)

ACTION REQUIRED:

The Working Group is invited to:

- Review the activities of TC WGDRR conducted in 2021

- Approve the recommendations and AOPs with the related budget of WGDRR in 2022

APPENDIX:

- Progress Report on activities of Working Group on WGDRR in 2021

- Proposal Plans for Implementation in 2022

ANNEX

- Implementation Status Success Indicators of WGDRR Annual Operating Plans in 2021

- Proposal on the implementation status Success Indicators of WGDRR Annual Operating Plans in 2022.

# APPENDIX

# Progress Report on activities of Working Group on WGDRR in 2021

# Introduction

The Working Group of Disaster Risk and Reduction  (WGDRR) continued to implement a series of projects according to the plan outline from the 53th TC Session. However, most of the face to face programs or projects are hindered by the COVID travel restrictions and was replaced by virtual meetings.

# Components of the WGDRR

WGDRR Member (Focal points)

| Chair | Dr. Sang Kwon Lee (Republic of Korea) |
| --- | --- |
| Vice Chairs | Mr. Marcus Aydlett (USA) Mr. Yuntae Kim (Republic of Korea) |
| Members | National Committee for Disaster Management (Cambodia) Mr. Wang Yawei (China) Mr. Kim Chol (DPR Korea) Mr. W Kong (Hong Kong, China) Mr. Soshi Murakawa (Japan) Mr. Norio Egawa (Japan) Ms. Shoko Kabuto (Japan) Mr. Shuhei Yasumatsu (Japan) Ms. Akhom Thammalangsy (Lao PDR) Mr. Ho Su Hon (Macao, China) Ms. Che Siti Noor bint koh Poh Lee (Malaysia) Mr. Bernardo Rafael R Alejandro IV, CESO IV (Philippines) Mr. Chihun Lee (Republic of Korea) Mr. Cheong Wee Kiong (Singapore) Mr. Saharat Wongsakulwiwat (Thailand) Mrs. Nguyen Thi Xuan Hong (Vietnam) |

# Organization of the 16th Working Group Disaster Risk and Reduction Virtual Meeting in Nov 2021

A video conference for the 16th Working Group meeting of ESCAP/WMO Typhoon Committee (TC) Working Group on Disaster Risk and Reduction (WGDRR) was organized by the National Disaster Management Institute (NDMI)on November 5, 2021 to discuss on the implementation status of the Annual Operation Plan in DRR aspects.

The meeting was convened by Dr Yuntae Kim, Vice Chair of WGDRR, with around 30 members and representatives from ESCAP, WMO, ADRC, Thailand, Malaysia, Lao PDR, Vietnam, USA, China (Shanghai, Hong Kong and Macau) and TCS participating. Dr Chihun LEE from NDMI was the moderator of the meeting.

During the meeting, the 2021 AOP implementation status was reviewed as follow

- AOP1. Capacity Building / Knowledge Sharing (NDMI)

  - Initially a seminar regarding capacity building was proposed to be held in Palau in August 2021.  Due to the outbreak of COVID-19 around the world, NDMI decided to postpone the seminar to 2022.

- AOP2. Setting up Early Warning and Alert System (NDMI)

  - Since 2013 NDMI has launched the project for strengthening capabilities of disaster risk reduction with various countries.  Similar project in Lao PDR was implemented in 2021. Feasibility studies such as site visit, land survey and meetings with local office was conducted and it was planned to install early warning and alert systems in Houaphanh and Xaisomboun Province in 2022.

- AOP3. WGDRR Annual Meeting

  - Owing to the COVID situation, WGDRR annual meeting has been using online mode since 2020. If the situation in 2022 permits, it will get back to face to face meeting in Korea. If not, it will still be online meeting.

- AOP4. Benefit Evaluation of Typhoon DRR (STI)

  - Dr. Shengming Tang from Shanghai Typhoon Institute (STI), China Meteorological Administration presented the progress of the benefit Evaluation of Typhoon DRR.

  - The project named “Benefit evaluation of typhoon disaster prevention and preparedness” aims to promote the research relating to this topic. Recent work focused on development and improvement of more specific level in a region on risk assessment technique and the potential risk assessment model’s resolution.

  - STI will continue to work on the verification of the empirical rainfall estimation model for Tropical Cyclones over Western North Pacific for the needs of assessing the long-term risk (STIRM) as well as multi-scale modelling and validation of Tropical Cyclone rainstorm waterlogging using multi-source precipitations. Furthermore, a novel wind field dynamical downscaling method (STIDM, Shanghai Typhoon Institute Downscaling Model) based on aerodynamical parameters (wind speed-up ratio) of the two-dimensional terrain was proposed.

- AOP5. Sharing Information related to DRR (NDMI)

  - WGDRR will continue to exchange information and experience related to DRR through the forum on the TC website. Members are welcome to upload all kinds of DRR information such as data, video clips to the TC website.

- AOP6. Making Education Videos related to DRR (HKO)

  - A video about “Fujiwhara Effect” was translated into English with voiceover and subtitles as the coming education video related to DRR.  Hong Kong Observatory shared the video during the meeting and no further comment was received from the members.  The video was uploaded to the Typhoon Committee website for members to use on public education on DRR.

- AOP7. Seminar for TC Crowd-sourcing high density non-conventional weather data (HKO)

  - Referring to the last WGDRR annual meeting, it was originally planned to conduct a face-to-face seminar (around 3 days) in the 4th Quarter of 2021 for experience sharing on concept and methodology of Tropical Cyclone crowd-sourcing high density non-conventional data.  However, as the COVID-19 pandemic remained, it was considered still not suitable to host such face-to-face meeting due to safety and travelling considerations.  While it was uncertain how long the pandemic would last for, instead of further postponement, HKO proposed to arrange online seminar in replace of the face-to-face seminar.  The online seminar will compose of two sessions on sharing the concept and experience of developing "My Weather Observation" and "Micro-climate Weather Station" by HKO.  The members agreed with HKO’s proposal.

During the meeting, the  WGDRR 2021 Budget Status was reviewed as follow

The only expected expenditure for 2021 DRR was the expected production fee USD1,735 of the educational video by Hong Kong Observatory. AOP6

| Project No | Name of Project | Proposed Budget (USD) | Expected Expenditure (USD) |
| --- | --- | --- | --- |
| AOP1 | Capacity Building/Knowledge Sharing in DRR | $10,000 | -- |
| AOP2 | Installation of Early Warning System related to typhoon disasters | Funded by NDMI | -- |
| AOP3 | WGDRR Annual Meeting | Funded by NDMI | -- |
| AOP4 | Benefit Evaluation of Typhoon Project | $6,000 | $0 |
| AOP5 | Sharing Information related to DRR | No need | -- |
| AOP6 | Making video related to DRR | $2,000 | $1,735 |
| AOP7 | Seminar for TC Crowd-sourcing high density non-conventional weather data | $12,000 | $0 |
|  | Total | $30,000 | $28,265 |

The participants expressed their appreciation to National Disaster Management Institute (NDMI) for their kind contribution and continued support on WGDRR activities and Hong Kong Observatory for making educational videos for the past years.

The participants extended their further appreciation to the Working Group Chairs, Dr. Yuntae Kim and Mr. Marcus Aydlett for their contribution and effort in the past years.

# Proposal Plans for Implementation in 2022

Further  (AOPs) for 2022 was proposed by WGDRR during the meeting.  These will be subjected to the final approval during the WGDRR parallel meeting on the 16th IWS.

# Report of the plan of NDMI’s 2022 Global Disaster Risk Reduction Project( AOP2)

Upon finishing the Lao PDR project, NDMI was asked to launch the project again with the Philippines.  Toledo City and Municipality of Dumanjug in the province of Cebu are decided as target areas for the project after the pre-feasibility study.

# Discussion on the continuity of STI( AOP4) and HKO’s projects( AOP6 &AOP7)

STI will continue the" Benefit Evaluation of typhoon disaster prevention and preparedness" project in 2022. However, as the COVID19 situation still going on, foreign scientists cannot come to Mainland China for research. STI will think of a fellowship format that works best for the projects.  Online seminars with financial incentives for the lecturers or video making may be used. Dr Tang will help to consult this and the related budget with the STI working group especially Ms Peiyan Chan. The final proposal will be presented during the IWS meeting in December.

HKO will continue to contribute educational videos related to DRR with English translation in 2022.  An online seminar, composing of two sessions on sharing the concept and experience of developing "My Weather Observation" and "Micro-climate Weather Station", will be held by HKO after the 54th TC session, i.e. around Quarter 1 to Quarter 2 of 2022.  The exact date will be confirmed at a later time.

# WGDRR AOP 2022 and Budget

| Project No | Name of Project | Working Plan 2022 | Proposed Budget (USD) |
| --- | --- | --- | --- |
| AOP1 | Capacity Building/Knowledge Sharing | Knowledge Sharing meeting will continue in Palau if situation permits. | $10,000 |
| AOP2 | Installation of Early Warning System related to typhoon disasters | Will implement a new project in Toledo City and Municipality of Dumanjug in Philippines | Funded by NDMI |
| AOP3 | WGDRR Annual Meeting | Face to face meeting in Korea if situation permits. | Funded by NDMI |
| AOP4 | Benefit Evaluation of Typhoon Project | Fellowship and online seminar. To be finalized by STI | $6,000 |
| AOP5 | Sharing Information related to DRR | Sharing information in TC website forum. | No need |
| AOP6 | Making video related to DRR | Making more educational videos by HKO. | $2,000 |
| AOP7 | Seminar for TC Crowd-sourcing high density non-conventional weather data | Hosting an online seminar by HKO, after the 54th TC Session in 2022. | No need |
|  | Total |  | USD18,000 |

# ANNEX

# Implementation for WGDRR AOPs in 2021 with the success indicators

| SP's KRA and SG | NO | Objective | Action | Other WGs Involved | TCS Responsibility | Quarter Completed | Project leader/Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed YES/NO |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KEA3 KRA4 KRA5 | 1 | Capacity Building /Knowledge Sharing | To organize an expert team to Palau for DRR information and capacity building exchange | Invite other WGs to join | Coordination and participation | Third | NDMI And participating members | Conducted the Mission in the selected member state | USD10,000 | NDMI and TCTF | No |
| KRA2 KAR3 KRA4 KRA5 | 2 | Installation of warning systems related to typhoon disaster | To develop and improve the installed EW and Alert Systems in the members’ state in order to improve the capacities of resilience for typhoon related disaster |  | Coordination | Fourth | NDMI | NDMI assigned experts to Laos and Vietnam to install and maintain the systems | Unspecified | NDMI | Yes |
| KRA1 KRA4 KRA5 | 3 | Organizing the WGDRR Annual Meeting | To organize the annual meeting to follow up on the working group’s activities and information exchange | AWG Members | Coordination and participation | Second | NDMI and TC DRR Members | The meeting was held in ROK | Unspecified | NDMI | No |
| KRA1 KRA4 KRA5 | 4 | Benefit Evaluation of Typhoon Project | To promote the research concerning benefit evaluation of typhoon disaster prevention and preparedness. |  | Coordination and participation | Second/ Third | STI, China | Conducted a research fellowship for TC Member in STI, China | USD$6,000 | TCTF | No |
| KRA2 KRA3 KRA4 KRA5 | 5 | Sharing information related to disaster risk management | To share information such as policies or mechanism related to DRR among TC Members via the forum established on TC Website |  | Establishment of the forum on TC website for facilitating the information sharing | Fourth | NDMI and TCS | Members shared the information on the forum | No need |  | Yes |
| KRA2 KRA$ KRA4 KRA5 | 6 | Making educational video related to DRR | To produce a video related to DRR education for raising public awareness. |  | Coordination | Third/ Fourth | NDMI | Completed the video with English subtitle and voiceover and shared with TC Member | USD1,735 | TCTF | Yes |
| KRA2 KRA3 KRA4 KRA5 | 7 | Seminar for TC Crowd-sourcing high density non-conventional weather data | HKO organize a Seminar and WG to coordinate the Member to take part in |  | Coordinate | Fourth | Hong Kong and participating members | The Seminar was successfully held in Hong Kong | USD$12,000 | TCTF | No |

  - KRA 1:  Enhance capacity to monitor mortality and direct economic loss caused by typhoon-related disasters.

  - KRA 2: Enhance capacity to generate and provide accurate, timely and understandable information using multi-hazard impact-based forecasts and risk-based warnings.

  - KRA 3: Improve typhoon-related flood control and integrated water resource management.

  - KRA 4: Strengthen typhoon-related disaster risk reduction activities in various sectors, including increased community-based resiliency with better response, communication, and information sharing capability.

  - KRA 5: Enhance Typhoon Committee’s Regional and International collaboration mechanism.

ANNEX

# Proposal for WGDRR AOPs in 2022 with the success indicators (to be discussed in the 16th IWS parallel meeting)

| SP's KRA and SG | NO | Objective | Action | Other WGs Involved | TCS Responsibility | Quarter Completed | Project leader/Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed YES/NO |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KEA3 KRA4 KRA5 | 1 | Capacity Building /Knowledge Sharing | To organize an expert team to Palau for DRR information and capacity building exchange | Invite other WGs to join | Coordination and participation | Third | NDMI And participating members | Conducted the Mission in the selected member state | USD$10,000 | NDMI and TCTF |  |
| KRA2 KAR3 KRA4 KRA5 | 2 | Installation of warning systems related to typhoon disaster | To develop and improve the installed EW and Alert Systems in the members’ state in order to improve the capacities of resilience for typhoon related disaster |  | Coordination | Fourth | NDMI | NDMI assigned experts to Philippines to install and maintain the systems | Unspecified | NDMI |  |
| KRA1 KRA4 KRA5 | 3 | Organizing the WGDRR Annual Meeting | To organize the annual meeting to follow up on the working group’s activities and information exchange | AWG Members | Coordination and participation | Second | NDMI and TC DRR Members | The meeting was held in ROK | Unspecified | NDMI |  |
| KRA1 KRA4 KRA5 | 4 | Benefit Evaluation of Typhoon Project | To promote the research concerning benefit evaluation of typhoon disaster prevention and preparedness. |  | Coordination and participation | Second/ Third | STI, China | Conducted a research fellowship for TC Member in STI, China. /Organized online seminar | USD$6,000 | TCTF |  |
| KRA2 KRA3 KRA4 KRA5 | 5 | Sharing information related to disaster risk management | To share information such as policies or mechanism related to DRR among TC Members via the forum established on TC Website |  | Establishment of the forum on TC website for facilitating the information sharing | Fourth | NDMI and TCS | Members shared the information on the forum | No need |  |  |
| KRA2 KRA$ KRA4 KRA5 | 6 | Making educational video related to DRR | To produce a video related to DRR education for raising public awareness. |  | Coordination | Third/ Fourth | NDMI | Completed the video with English subtitle and voiceover and shared with TC Member | USD2,000 | TCTF |  |
| KRA2 KRA3 KRA4 KRA5 | 7 | Seminar for TC Crowd-sourcing high density non-conventional weather data | HKO organize an online Seminar for members to take part in |  | Coordinate | First/Second | Hong Kong and participating members | The Seminar was successfully held in Hong Kong | No need |  |  |

  - KRA 1:  Enhance capacity to monitor mortality and direct economic loss caused by typhoon-related disasters.

  - KRA 2: Enhance capacity to generate and provide accurate, timely and understandable information using multi-hazard impact-based forecasts and risk-based warnings.

  - KRA 3: Improve typhoon-related flood control and integrated water resource management.

  - KRA 4: Strengthen typhoon-related disaster risk reduction activities in various sectors, including increased community-based resiliency with better response, communication, and information sharing capability.

  - KRA 5: Enhance Typhoon Committee’s Regional and International collaboration mechanism.