APPENDIX V
TC47 REPORT

REPORT OF ACTIVITIES OF WORKING GROUP

ON DISASTER RISK REDUCTION (WGDRR) IN 2014

1. The 9thWGDRR Annual Meeting

The 9th Working Group on Disaster Risk Reduction Annual Meeting was held in Seoul, Republic of Korea from 26 May to 27 May. Total 7 member countries including Macao, China, Malaysia, Hong Kong, China Republic of Korea, Thailand, USA (Guam), and Vietnam participated on the workshop. Also, there were participants from international organizations such as ADRC (Mr. JunjiMoriwaki), UNESCAP (Ms. Yejin Ha), and Tohoku University (Dr. Yuichi Ono).The main theme of the 9th WGDRR Annual Workshop was “Past, Present, and Future of WGDRR”. In the workshop, the ways of strengthening on international cooperation for DRR were mainly discussed. With reference to the main theme, Dr. Shim, Jae Hyun from NDMI introduced the history of WGDRR and reviewed the main themes in the past annual meetings since 2006. Through the review, he suggested the future ways of WGDRR which include 1) Long-term development strategy for WGDRR annual meeting, 2) Expansion of TCDIS, 3) International Cooperation among member countries for DRR.

The presentations in the 9th WGDRR Annual Workshop were as follow;

1) Review of WGDRR Action Sheet (Mr. OlavoRasquinho)

2) Past, Present, and Future of WGDRR (Dr. Shim, Jae Hyun)

3) Introduction of NOAA and International Cooperation Research Strategy (Mr. Raymond Tanabe)

4) Prospect of International Cooperation on Natural Disaster Risk Reduction (Dr. Kim, Chang Wan)

5) Media Report Guideline on Disaster and introduction on AMCDRR (Dr. Yuichi Ono)

6) Member reports

: Hong Kong, China; Macao, China; Malaysia; Republic of Korea;Thailand,;USA(Guam),;and Vietnam.

7) Introduction of NDMI project (Transfer of New Technologies for Disaster Prevention and Safety)

(Dr. Chihun Lee)

8) Smart Disaster Management Technology (Smart Big Board and Big Data Analysis)

(Dr. Hong, Sung Jin)

9) Introduction of New-Version TCDIS and Trial Performance (Dr. Kim, Jitae)

10) Activities of UNESCAP in Korea (Ms. Ha, Yejin)

11) Development of Web-GIS Public Safety Map (Mr. Park, Kyung Chan)

2. The 2014 Northern Mindanao Project

The Northern Mindanao project, launched in 2013 upon a request of the PAGASA of the Philippines, completed its second phase in 2014. The project aims to help the Philippines reduce flash flood-related risk, especially for Cagayan De Oro City in the Northern Mindanao area, through installation of the Flash Flood Alert System(FFAS) and the Automatic Rainfall Warning Systems(ARWS). The city was one of the areas hit hard by Typhoon Washi in 2011. So far the FFAS has been installed at the PAGASA in Manila as well as its regional office in Cagayan De Oro. In addition, two rainfall gauges, one water level gauge, and two warning posts have been installed along with the Cagayan De Oro River. The FFAS receives real time-based monitoring data from this equipment, and forecasts the occurrence of flash flood in three hour advance. The Northern Mindanao project will be completedin 2015, and NDMI is seeking to expand a disaster risk reduction project to other member countries.

3. The WGDRR Parallel Session in 9th Integrated Workshop

During the 9th Typhoon Committee Integrated Workshop held in United Nations Conference Center, Bangkok, Thailand from 20 to 24 October 2014, the Working Group on Disaster Risk Reduction (WGDRR) had a two-day parallel session on 21 through 22October 2014.

There were15 representativesfrom 9 Members (i.e. China; DPR Korea; Hong Kong, China; Lao PDR; Malaysia; Republic of Korea; Thailand; USA (Guam and Hawaii); Vietnam), ADRC, UNESCAP and TCS attending the WGDRR parallel sessions.

The WGDRR parallel session exchanged the information on priorities and key areas; reviewed the progress onthe implementation of the AOPs for 2014; discussed the 2015 WGDRR AOPs and the budget; reappointed a chair and a vice chair of the WGDRR; discussed how to participate in the 3rd UN World Conference on Disaster Risk Reduction.

3. The review of WGDRR activities in 2014 AOPs

(AOP1) Extend the WEB GIS based TCDIS

WEBGIS based TCDIS started in 2006 and was upgraded to second version in 2014. In 2014 version of TCDIS, it included new website design in TCDIS, improvement on the search option for past similar Typhoon, and display of historical regional damage. There has been difficulty for NDMIin collecting information from member countries. In this regard, it is suggested that member countries would provide the past disaster damage data and other related data through member country report. It is recognized that TCDIS is an important base and suggested to report the progress of each year in the TC Session.

(AOP2) Provide the training program for disaster prevention technologies and policies including WGTCDIS

The Expert mission team including NDMI and TCS visited Guam (DHS, Department of Homeland Security)on September 2014. During the expert mission, following items were discussed;

1) Training on TCDIS

2) Urban flood analysis and Korea community safety map

3) Introduction of DSI (Disaster Scientific Investigation)

4) Use of radar measurement for rainfall-induced disaster response

With reference to the contents of expert mission, Member countries can select and request the training program. Member countries for expert mission in 2015 will be discussed in 47th session in Bangkok, Thailand.

(AOP3) Promote the international cooperation research

The 2014 Northern Mindanao Project for Philippines was implemented by NDMI and in this project, Flash Flood Alert System (FFAS) and Automatic Rainfall Warning System (ARWS) were installed in Cagayan de Oro, Philippines.The Northern Mindanao Project will be completed in 2015. The project aims to expand the installation of ARWS (Automatic Rainfall Warning System) in Cagayan de Oro and enhance the function of FFAS (Flash Flood Alert System).NDMI proposed to all TC members to join this project similar to Philippines and suggested TC members who are interested in the project can submit their proposal before May 2015.

(AOP4) Application of SWIdge (Hong Kong) to member countries

SWIdget is a widget, which allows users anywhere on the globe to obtain local severe weather warnings issued by official weather services in real time. In 2014, there was not much progress without new member subscribing to the SWIdget initiative. There are 7 member countries of current SWIdget providers including China (Guandong); Hong Kong, China; Macao, China; Malaysia; Republic of Korea; Singapore; and USA (Guam). HKO will continue to encourage members to join the initiative. As warning information dissemination technology and delivery platformsevolve, SWIdget will only be one of many available options open for members and no significant resource input is expected for further SWIdget development.

(AOP5) Benefit evaluation of Typhoon disaster prevention and preparedness project

The CMA proposed this project in 45th TC session, but not much progress was reported so far. Nevertheless, the AOP5 will be continuedin 2015, and the members agreed on it.

(AOP6) Setting up community weather stations for raising public awareness on climate change and extreme weather

This project was proposed by HKO and found useful to promote public awareness. The HKO extended it to community weather observing scheme (CWOS), which was well received by the public. It was recognized that the similar concept like ICWOscan be also extended to other TC members. In last November, a training workshop on iCoWin was held in Hong Kong, China, for participants from Viet Nam and Lao PDR.  Participants from Lao PDR and Viet Nam have identified sites to install iCoWin weather station and plan to implement them in 2015. DPRK expressed their interest in taking part in this project in 2015. The HKO can plan further trainingin Hong Kong, China,forother TC members subject to funding available.

(AOP7) Supporting Synergized Standard Operation Procedure (SSOP) project related to disaster risk management

The mechanism meeting was held in Bangkok, Thailand in last October. The TC Secretariat participated inand presented the AOPs of the WGDRR. The possibility of extension of the expert missions and the iCo-Win project to the PTC, and the formulation of experience sharing tools/materials between the TC and the PTC was discussed during the meeting.

(AOP8) Media response to build the trust with media

The NDMI took an initiative on this AOP, and reported that there was a positive action taken by the journalist associations in Korea. They agreed upon the disaster reporting rules such as reporting news not to increase psychological uncertainty, prohibiting the interview with victims and their families under pressure, and verifying the information by experts. Acknowledging difficulty in building trust with the media, especially on disaster-related reports, the WGDRR agreed not to continue this AOP in 2015.

(AOP9) Making the information more understandable to the public and make them react

This was led by the HKO, and aimed to produce a video for raising the public awareness on danger associated with tropical cyclones (heavy rain, high winds and waves,storm surges). It has made progress in 2014 and the prototype video is readyin early 2015.

(AOP10) Providing policy message on two events namely AMCDRR in Bangkok on 22-26 June 2014, and the Third UN World Conference on Disaster Risk Reduction in 2015

In 2014, WGDRR was not able to make a contribution to the AMCDRR held in June 2014, but agreed to hold a side event in the Third UN World Conference on Disaster Risk Reduction. The NDMI and the TC submitted application, and the committee confirmed the participation in the Public Forum. The discussion on a theme of the event, a selection of invited speakers, and etc. is under progress.

4. Implementation status of the WGDRR AOP 2015

AOPs 8 and 9 were completed in 2014 and AOPs 1-7, 10 in 2014 will be continued in 2015

[AOPsto be continued in 2015]

(AOP1) Extend the WEB GIS based TCDIS

(AOP2) Provide the training program for disaster prevention technologies and policies including

WGTCDIS

(AOP3) Promote the international cooperation research

(AOP4) Application of SWIdge (Hong Kong) to member countries

(AOP5) Benefit evaluation of Typhoon disaster prevention and preparedness project

(AOP6) Setting up community weather stations for raising public awareness on climate change

and extreme weather

(AOP7) Supporting Synergized Standard Operation Procedure (SSOP) project related to disaster

risk management

(AOP8) Providing policy message on the 3rd UN World conference on Disaster Risk Reduction

in 2015

5. Confirmed budget proposed for WGDRR activities in 2015

WGDRR proposed the requests of US$ 26,000 allocated TCTF in 2015 to support the WGDRR activities including:

i) To allocate US$ 8,000 budget of TCTF in 2015 for supporting WGDRR participating in next TC Integrated Workshop.

ii) To allocate US$ 5,000 budget of TCTF in 2015 for supporting community based weather station pilot project offering training to interested members to facilitate them to install the weather stations and to provide technical documentation on installation, maintenance and data processing and display.

iii) To allocate US$ 6,000 budget of TCTF in 2015 for supporting TCS, to take part in the WGDRR Expert Missions.

iv) To allocate US$ 7,000 budget of Special Request Budget in 2015 for participation of the WGDRR in the 3rd UN World Conference on Disaster Risk Reduction.

6. Conclusion of WGDRR

On the basis of the information provided by the Members and findings of the parallel session on WGDRR, the following conclusions were reached:

i)WGDRR recognized the necessity of continuous collection of disaster information from the Member countries for the WGTCDIS. Encouragement to the members to collect and share disaster information will be continued in 2015.

ii)National Disaster Management Institute (NDMI) will upgrade and expand the WGTCDIS in 2015.

iii)The expert mission was successfully conducted in Guam, USA in 2014 to provide updated information on the operation of WGTCDIS and exchange information regarding new technology and policy related to field of DRR by NDMI and TCS. The expert mission will be conducted upon requests of the member countries in 2015. Member countries in WGDRR agreed to collect the demands from the members on the expert mission.

iv)The project to promote the international cooperation research for disaster risk management, which led by NDMI, will continue in 2015. The NDMI will dispatch the experts of Republic of Korea to the Philippines for installing the Automated Weather Station (AWS) and Flash Flood Alert System (FFAS) in Cagayan de Oro, Mindanao Island in Philippine.

Note: NDMI proposed to all TC Members to submit their proposal two years in advance if they want to join this project similar to Philippines.

v)WGDRR acknowledged the achievement of the AOP 6 led by Hong Kong, China, including its effort to raise public awareness on weather through community weather observing scheme and the training workshop to be held at Hong Kong Observatory in early November. DPR Korea expressed an interest in taking part in the project in 2015 and Thailand also requested such training opportunities be made available for other Members as well. Regarding the AOP4, not much progress was made and there might be a need to review whether this AOP should continue given the evaluation of other warning dissemination technology. As for AOP 9, the project of producing a video for raising public awareness of danger associated with tropical cyclones will be completed in early 2015.Subject to further comments from TCS, the video will be shared among Typhoon Committee Members. TCS has reallocated the budget according to the recommendationby the WGDRR parallel session during 9thIWS Meeting, but eventually the final actual expenditure did not exceed the original budget.

vi)As no representative from China that is responsible for the AOP 5 attended the session, China will send the report related to the progress of the AOP 5 progress until the next session. In addition, China requested for the continuity of AOP 5 but without necessity to claim for the budget in 2015, and the Members agreed on it.

vii)The mechanism meeting to support the SSOP project was held in Bangkok, Thailand on 9-10 October 2014. The WGDRR noted that there was a demand for an extension of the expert missions and theiCO-Win project to the PTC members. The WGDRR members will take it into consideration in 2015.

viii)Regarding the AOP 8, NDMI reported that there was a positiveaction taken by the Media in the Republic of Korea. The WGDRR acknowledgethe difficulty of building trust with the Media on the disaster-related reports. The AOP 8 will not be continued in 2015.

ix) WGDRR acknowledged that the TCS and the NDMI submittedapplication of participating in Public Forum at the WGDRR. As there was a consensus among the WGDRR members about significance of the UNWCDRR, the WGDRR agreed to request special budget for this in 2015. The organizing cost for holding public forum to the Committee for the 3th UNWCDRR has been paid by TCTF at the end of November.

x)WGDRR reappointed Dr. Yeo Woonkwang as the chair of group whileMs Leong Fong Peng as a vice chair of the group. Dr. Yeo suggested appointing Dr. Shim, Jaehyun as vice chair as well to deputize for him in his absence. The WGDRR agreed on his suggestion.

7. Recommendation of WGDRR

On the basis of the information provided by the Members and deliberations, the WGDRR Members made the followingrecommendations:

i)To allocate US$ 26,000 budget of TCTF in 2015 for a) supporting the WGDRR participating in the next TC Integrated Workshop; b) Supporting the community based weather station pilot project to provide a training workshop in Hong Kong or dispatch experts to interested members by Hong Kong to install the weather stations and to provide technical documentation on installation, maintenance and data processing and display; c) supporting TCS participating on WGDRR expert mission and d) support to conduct a lecture by the WGDRR and to organize the participation in the 3rd  UN World Conference on Disaster Risk Reduction.

ii)To encourage the TC members to collect and share the disaster information for extending TCDIS; the TCDIS will be continually upgraded and extended in 2015.

iii)To collect the demands of expert mission from the members until the next annual session.

iv)To continue promotion of the internationalcooperation researchthrough the Northern Mindanao Project: any member of TC is welcomed to submit a proposal to the NDMI.

v)To contact the WGDRR Focal Point of China for learning the progress of AOP5 as to the continuity of this project (but without necessity to claim for the budget)in 2015.

vi)To provide training on community based weather station projectin 2015.

vii)To explore opportunity for PTC members to take part in the iCO-Win project and to exchange experience in engagingcommunity to be aware of weather threats and climate change.

viii)To facilitateparticipation of WGDRR in the 3rd UN World Conference on DRR and recognize the advance payment USD800 for the organizing cost of holding public forum.in the mentioned Conference.

Appendix 1. WGDRR AOP 2014 Implementation Status

Appendix 2. WGDRR AOP 2015

Appendix 1. WGDRR AOP 2014 Implementation Status

| SPs KRA and SGs | Objective Number | Objective | Action | Other WG’s | TCS Responsibility | Expected Quarter Completed | Other Organi- zations Involved | Success Indicators | Funding Required | Funding Sources | Completed Yes or No |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 4 KRA 5 SG 4b SG 4c | 1 | Extending the WGTCIDS | (i)Collect disaster information from TC Members (ii) Upgrade the search option for similar Typhoon in WGTCDIS | TCS | Assist in collecting disaster information from Members | Ongoing | NDMI | Upgrade the earch option for finding similar Typhoon in WGTCDIS |  | NDMI, Korea | Yes |
| KRA 4 KRA 5 SG 4b SG 4c SG 5b | 2 | Provide the training program | Perform Expert Mission for training disaster prevention technologies and policies including WGTCDIS | TCS | Assist in planning and performing the expert mission | Ongoing | NDMI | Send expert team to USA(Guam) | US $ 4,000 | NDMI, Korea and TCTF | Yes |
| KRA ALL SG ALL | 3 | Promote the international cooperation research | install the Flash Flood Alert System (FFAS) and AWS in Mindanao, the Philippines |  | Assist in planning and performing theinternational cooperation research | Ongoing | NDMI PAGASA | Complete the second phase of the Northern Mindanao project |  | NDMI, Korea | Yes |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 4 | Application of SWIdget to Member countries | Promote and extend the dissemination of warnings and alerts by Members through SWIC (Severe Weather Information Center) | - | Assist in liaising with focal points | Ongoing | HKO | Disseminate the warnings/alerts through SWIdget |  | HKO, Hong Kong | Yes |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 5 | Setting up of community weather stations for raising public awareness on climate changes and extreme weather | (i) Liaise with Members on requirements and ways to take part in the project (ii) Offer training in Hong Kong, China for Viet Nam and Lao to implement the community weather stations | - | Assist in liaising with focal points ad provide logistic support for the expert visits | Ongoing | HKO | i)Provide trainings on the iCoWin ii) Extended to community weather observing scheme | US $5,000 | TCTF | Yes |
| SP’s KRA and SG | Objective Number | Objective | Action | Other WG’s | TCS Responsibility | Expected Quarter Completed | Other Organi -zations Involved | Success Indicators | Funding Required | Funding Sources | Completed Yes or No |
| KRA4 KRA5 KRA7 SG4b SG5a SG6b | 6 | Provide benefit evaluation of Typhoon disaster prevention and preparedness | (i) survey and evaluate the response of government, department, company and person to typhoon disaster (ii) survey and evaluate the benefit of different response |  | Assist in planning and performing theinternational cooperation research | Ongoing | CMA | Complete collecting response of government and departments, evaluation report finalized | US $2,000 | TCTF | Yes |
| KRA ALL SG ALL | 7 | Support the Synergized Standard Operation Procedure (SSOP) project |  | WGM WGH TCS |  | Ongoing |  |  |  |  | Yes |
| KRA4 SG5a SG6b | 8 | Research media response how to build the trust with media | research the media response on the disaster |  |  | Fourth | NDMI | Provide the results of the research in 9th IWS |  |  | Yes |
| KRA4 SG5a SG6b | 9 | Increase public awareness by making the information more understandable to the public and making them react | (i) make the educational video for the public (ii) collect the disaster information of member countries | TCS | Assist in collecting disaster information of member countries | Fourth | HKO | Complete the development of educational video for the public | $6,000 | HKO, Hong Kong Special request budget | Yes |
| KRA4 KRA7 SG5a SG6b | 10 | Providing the message on two events namely AMCDRR (exhibition booth and side event) in Bangkok on 22-26 June 2014 and 3th UN World Conference on Disaster Risk Reduction in 2015 | (i) prepare WGDRR booth in AMCDRR (ii) prepare WGDRR booth in AMCDRR | TCS | Assist in planning and performing booth presentation in conference | Ongoing | NDMI TMD | Operate the booth in AMCDRR and Submit application for participating in 3th UN World conference | $4,000 | TMD, NDMI, and TCTF | Yes |

Appendix 2. WGDRR AOP 2015

| SPs KRA and SGs | Objective Number | Objective | Action | Other WG’s | TCS Responsibility | Expected Quarter Completed | Other Organi- zations Involved | Success Indicators | Funding Required | Funding Sources | Completed Yes or No |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 4 KRA 5 SG 4b SG 4c | 1 | Extending the WGTCIDS | (i)Collect disaster information from TC Members (ii) Upgrade the search option for similar Typhoon in WGTCDIS | TCS | Assist in collecting disaster information from Members | Ongoing | NDMI | i) collect disaster information from Members ii)Upgrade the search option for finding similar Typhoon in WGTCDIS |  | NDMI, Korea |  |
| KRA 4 KRA 5 SG 4b SG 4c SG 5b | 2 | Provide the training program | Perform Expert Mission for training disaster prevention technologies and policies including WGTCDIS | TCS | Assist in planning and performing the expert mission | Ongoing | NDMI | Send expert team to Members | US $ 6,000 | NDMI, Korea and TCTF |  |
| KRA ALL SG ALL | 3 | Promote the international cooperation research | install the Flash Flood Alert System (FFAS) and AWS in Mindanao, the Philippines |  | Assist in planning and performing theinternational cooperation research | Ongoing | NDMI PAGASA | Complete the last phase of the Northern Mindanao project |  | NDMI, Korea |  |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 4 | Application of SWIdget to Member countries | Promote and extend the dissemination of warnings and alerts by Members through SWIC (Severe Weather Information Center) | - | Assist in liaising with focal points | Ongoing | HKO | Disseminate the warnings/alerts through SWIdget |  | HKO, Hong Kong |  |
| KRA4 KRA5 KRA7 SG4b SG5a SG6b | 5 | Provide benefit evaluation of Typhoon disaster prevention and preparedness | (i) survey and evaluate the response of government, department, company and person to typhoon disaster (ii) survey and evaluate the benefit of different response |  | Assist in planning and performing theinternational cooperation research | Ongoing | CMA | Complete collecting response of government and departments, evaluation report finalized |  | CMA |  |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 6 | Setting up of community weather stations for raising public awareness on climate changes and extreme weather | (i) Liaise with Members on requirements and ways to take part in the project (ii) Offer training in Hong Kong, China for interested Members to implement the community weather stations | - | Assist in liaising with focal points ad provide logistic support for the expert visits | Ongoing | HKO | i)Provide trainings on the iCoWin ii) Extended to community weather observing scheme | US $6,000 | TCTF |  |
| KRA ALL SG ALL | 7 | Support the Synergized Standard Operation Procedure (SSOP) project |  | WGM WGH TCS |  | Ongoing |  |  |  |  | Yes |
| KRA4 KRA7 SG5a SG6b | 10 | Providing the message on the 3th UN World Conference on Disaster Risk Reduction in 2015 | Hold a seminar on DRR in the WCDRR | TCS | Assist in planning and performing booth presentation in conference | Ongoing | NDMI | Hold a seminar in3th UN World conference | $7,000 | TMD, NDMI, and TCTF | Yes |

SG1:  To enhance cooperation among TC Members to reduce the number of deaths by typhoon-related disasters by half in the ten years of 2006 – 2015 (using the ten years of 1990 - 1999 as the base line).

SG2:  To reduce the socio-economic impacts of typhoon-related disasters per GDP per capita by 20 per cent in the ten years of 2006- 2015 (using the ten years of 1990 - 1999 as the base line).

SG 3a:  To identify and explore the beneficial use of resources such as rainfall brought by typhoon.

SG 3b:  To study and promote the increasing use of typhoon-related beneficial effects among the Members.

SG 4a:  To provide reliable typhoon-related disaster information for effective decision making in risk management in various sectors.

SG 4b:  To strengthen capacity of the Members in typhoon-related disaster risk management in various sectors.

SG 4c:  To enhance international and regional cooperation and assistance in the field of disaster risk reduction.

SG 5a:  To promote and enhance culture of community-based disaster risk management among the Members.

SG 5b:  To promote education, training and public awareness of typhoon-related disasters among the Members.

SG 6a:  To facilitate RSMC capability to respond to the needs of the Members in forecasting and capacity building.

SG 6b:  To improve capacity of Members to provide timely and accurate user-oriented and friendly tropical cyclone products and information.

SG 6c:  To enhance capacity of Members' typhoon-related observation, monitoring, forecasting and warning.

SG 7a:  To strengthen the capacity of Typhoon Committee to effectively discharge its responsibilities and functions described in this Strategic Plan and completed its stated mission in accordance with the Typhoon Committee’s Statute.

SG 7b:  To mobilize available resources and engage collaborators for the implementation of the strategic goals.

KRA 1:  Reduced Loss of Life from Typhoon-related Disasters.

KRA 2:  Minimized Typhoon-related Social and Economic Impacts.

KRA 3:  Enhanced beneficial typhoon-related effects for the betterment of quality of life.

KRA 4:  Improved Typhoon-related Disaster Risk Management in Various Sectors.

KRA 5:  Strengthened Resilience of Communities to Typhoon-related Disaster.

KRA 6:  Improved capacity to generate and provide accurate, timely and understandable information on typhoon-related threats.

KRA 7:  Enhanced Typhoon Committee’s Effectiveness, Efficiency and International Collaboration.