## Sheet1
APPENDIX XVIII - Typhoon Committee Integrated Annual Operating Plan for Calendar Year 2009
Submitted by the Advisory Working Group - 21 January 2009
SG 1: To enhance cooperation among TC Members to reduce the number of deaths by typhoon-related disasters by half
(using the decade 1990-1999 as the base line to compare with the decade 2006-2015).
SG 2: To reduce the socio-economic impacts of typhoon-related disasters per GDP per capita by 20 per cent
(using the decade 1990-1999 as the base line to compare with the decade 2006-2015).
SG 3a: To improve the beneficial use of typhoon-related effects of typhoons by 10 per cent in water management by selected Members
(using the decade 1990-1999 as the base line to compare with the decade 2006-2015)
SG 3b: To promote increasing use of the typhoon-related beneficial effects among the Members
SG 4a: To provide reliable typhoon-related disaster information for effective policy making in risk management in various sectors.
SG 4b: To strengthen capacity of the Members in typhoon-related disaster risk management in various sectors
SG 4c: To enhance international and regional cooperation and assistance in the field of disaster risk reduction.
SG 5a: To promote and enhance culture of community-based disaster risk management among the Members
SG 5b: To promote education, training and public awareness of typhoon-related disasters among the Members
SG 6a. To strengthen RSMC capacity to respond to the needs of the Members in forecasting and capacity building
SG 6b. To improve capacity of Members to provide timely and accurate user-oriented and friendly TC products and information
SG 6c. To enhance capacity of Members' typhoon-related observation and monitoring
SG 7a: To strengthen the capacity of TCS to effectively discharge its responsibilities and functions described in the Terms
of Reference and support the Members in the implementation of the strategic goals
SG 7b: To strengthen the capacity for resources mobilization for the implementation of the strategic goals
Working Group on Meteorology
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
| 1 | Assessment of the impact of climate change on tropical cyclone frequency and intensity variation | (a)To make a simple collective report on frequency and intensity change of tropical cyclones (Tong Tin Ngai, Macao) (b) To form an expert team (Recommended members: Tong Tin Ngai, Jim, WJ Lee, CMA, MRI/JMA, HKO) (c) To form a critical assessment and make suggestions / interpretation for users |  |  | (1) 41st session (2) 41st session (3) 42nd session | HKO | (a) Distribution an overview report on the impact of the climate change on tropical cyclone frequency and intensity at 41st session (b) Publication of a serial evaluation scientific report under the name of Typhoon Committee since 42nd session | US $4,000 | Yes
| 2 | Development of typhoon information processing system (TIPS) | To hold a workshop on TIPS (jointly with EPS) Place: ROK | TRCG |  | Mid April / late Feb. | KMA | Improvement/establishment of TIPS by Members | US $6,000 | Yes
| 3 | Improvement of warning services for urban areas (coastal areas) | To develop a guideline for quantitative precipitation estimation (QPE) quantitative precipitation forecast (QPF) techniques and a regional storm surge forecasting system for urban areas | WGH, WGDPP |  | (1) second-third quarter (2) 42nd session |  | (a) Publication of a guideline for QPE/QPF (b) Dissemination of a regional advisory for storm surge forecasting
| 4 | Improvement of tropical cyclone forecasting skill of TC Members | To exploit and share the results of T-PARC by Members (evaluation of the impact of the T-PARC special observation on typhoons) | WGH, WGDPP |  | 41st session | JMA | Distribution of an evaluation report on the impact of the T-PARC special observation on typhoon
| 5 | Improvement of communication system in the TC area | (1) To upgrade the communication system in Members (prepared for WMO information system) (2) Upgrade the VSAT system in five countries (China) (3) Migration from A/N to BUFR (ROK offered to provide software support) |  |  | 4th quarter | CMA,KMA | (a) Number of Members prepared for WIS (b) Number of Members with new VSAT system (c) Completion of the migration in the Committee’s region | USD$3,000 | Yes
| 6 | Promotion of discussions among forecasters of TC Members during the approach of tropical cyclones | To set up an on-line forum for exchange of typhoon monitoring and forecasting information, consisting of experts of met., hydro. and DPP. |  |  | 2nd quarter | CMA | (a) Development of a guideline on the structure and operation of the forum (CMA) (b) Establishment of the forum
| 7 | Improvement of warning information dissemination | To hold a roving seminar jointly with TRCG on forecast techniques, warning dissemination and media skills (Hong Kong or Nanjing, China) | TRCG |  | 4th quarter | HKO,CMA | Origination of the workshop.
Working Group on Hydrology (WGH)
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 1 | Produce and use Flood Hazard Maps (FHMs) | To prepare and publish FHMs which are used by local people and municipalities for timely evacuations and planning | WGDPP | See above | (a) First (b) Second (c) Third (d) Fourth | ICHARM, JICA | (a) IDI requests members to submit reports on their activities, model produced FHMs, etc. （ICHARM & JICA conduct FHM follow-up seminar in Manila) (b) Each member submits reports to IDI (c) IDI to compile draft final report containing following items Outline and Background, Cooperative activities, Member’s activities, FHM example in each members, Conclusion (c) IDI presents draft final report at IWS (d) IDI compiles/publish final report of the project |  | (1) JICA (2) Members' own funds
KRA 1 SG1 | 2 | Establish debris flow and landslides warning system | Establish methodologies in TC region of using Critical Lines (CLs) for issuing evacuation orders/advices to communities against sediment-related disasters | WGDPP | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) NILIM, Japan requests members to write a report on their activites on model areas. (b) each member submits reports on requested activities (c) NILIM compiles reports including following items. Abstract, Outline, Review of methodologies for setting CLs, Achievement of members, Conclusion (c) NILIM to introduce draft final report at IWS (d) NILIM to finalize/publish final report of the project
KRA 1 SG 1 KRA 2 SG 2 | 3 | To improve flood forecasting capability and accuracy through On-the-Job Training (OJT) | Conduct OJT on flood forecasting through the use of models, observations, and past events |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (b) Malaysia in collaboration with TCS invites participants from TC members (b) 3 particiants will be identified (c) Selected participants prepare required data for the model sites (c) Malaysia reviews data and information on selected pilot areas (d) Malaysia conducts 3 week OJT for 3 participants in late 2009 | TCTF 3,000 USD to support intl. participants, and local funds to be prepared by Malaysia | TCTF
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 4 | Projects on Urban Flood Management in TC Region | *To enhance TC members' capacity on urban flood management *to prepare “Guidelines on flood management for urban planning and development in the Typhoon Area”, etc | WGM,WGDPP | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) MWR, China sends questionnaires on urban flood management practices in TC members (b) members send requested information to MWR c) China presents compiled information at IWS (d) specific areas for collabration, model area, etc. will be identified | Funding required from funding agencies to promote integrated approaches to urban flood management | (potential) ADB, JICA, KOICA
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 6b | 5 | Assessment System of Socio-economic Impacts of Water-related Disasters for Infrastructure | To provide an effective and/or optimum socio-economic flood control/management measure and reasonable preliminary damage forecast system for flood control/management infrastructure investment |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) ROK requests members to provide their own assessmen system on infrastructure investment, etc (b) ROK compiles information from the members (c,d) ROK conducts current status and assessment system analysis of domestic and abroad flood control measures
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 6 | Project on Hazard Mapping for sediment-elated disasters | To raise local people’s awareness for sediment-related disasters. To separate people and their properties from high-risk areas |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) NILIM, Japan will distribute a draft of guideline and opens Technical Help Desk. (b) Members will select model sites with topographical map & field survey c) the results will be reported at IWS
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 7 | Project on development and application of flood disaster preparedness indices | To promote the actions of local government bodies/communities to strengthen the level of preparedness for flood disasters, by applying a set of evaluation indices |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) Japan provides to members a draft evaluation system (a set of indices) and opens a THD (b) Members will select model municipalities or communities and test application of proposed evaluation system ( c) Members will report to Japan the results of evaluation together with comments for improvement of indices (d) the results will be discussed at next IWS
Working Group on DPP
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
KRA 4 SG 4b and 4c KRA 5 SG 5b | 1 | Promote value of WEB_GIS based TC DIS to TC Members | Provide WEB_GIS based TCDIS system to Members and explain the purpose and use of the WEB_GIS based TCDIS and to promote its benefits |  | Assist in planning the expert missions | First | ADRC, UN/ISDR, etc. | Complete expert missions to the Viet Nam to facilitate implementation of the WEB_GIS based TCDIS in the respective Member | US $12,000 | NEMA, Korea TCTF
KRA 4 SG 4b and 4c KRA 5 SG 5b | 2 | Enhance WEB_GIS based TCDIS and establish methodology to assess the socio-economic impacts of disasters | Conduct the 4th Meeting of WGDPP to brief Members on WEB_GIS based TCDIS and discuss on assessment of the social and economic impacts of natural disasters | WGM WGH | Plan, coordinate, organize and facilitate | Second | ADRC, UN/ISDR, etc. | Brief Members on how to provide input and maintain WEB_GIS based TCDIS as well as its potential applications and discuss on assessment of the social and economic impacts of natural disasters | US $30,000 | NEMA, Korea and TCTF
KRA 4 SG 4b and 4c KRA 5 SG 5b | 3 | Operational implementation of WEB_GIS based TCDIS | Maintain Hardware, Software of WEB_GIS based TCDIS System and upgrade disaster information and other contents by inputs from Members | WGM WGH | Assist in collecting necessary data from Members | Expect to go operational by March 2009 | ADRC, UN/ISDR, etc. | Complete each Member's disaster information in 2008 | US $30,000 for maintenance | NEMA, Korea and TCTF
KRA All SG ALL | 4 | Review progress of TCDIS project and enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Participate in a focused, integrated WGM, WGH, WGDPP, TRCG, and AWG Workshop with specific deliverables defined and to review progress of TCDIS project and future activities of WGDPP | WGM WGH WGDPP TRCG AWG RMG | Plan, coordinate, organize, and facilitate | Second or third |  | Discuss future activities of WGDPP, report on TCDIS and collaboration with other WGs
KRA 4 SG 4b and 4c KRA 5 SG 5b | 5 | Maintain and enhance WEB_GIS based TCDIS | Make presentation on WGDPP's Activities in 2009 |  | Assist in including presentation on the TC Session agenda | Fourth |  | Successful acceptance of WEB_GIS based TCDIS by TC Members
KRA 4 SG 4b and 4c KRA 5 SG 5b | 6 | To develop a conceptual framework consistent with Typhoon-related Hazard Early Warning Systems in conjunction with other WGs to make a link with the TCDIS | Prepare concept paper and proposal on program of action | WGM WGH TRCG AWG | Assist in collecting inputs from Members | Concept paper by First Qt. and initiate public education activities jointly with mission |  | Acceptance of concept paper and mission
Training and Research Coordinating Group (TRCG)
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
KRA 6 / SG 6b and 6c | 1 | To: (a) enhance Members' capability and capacity in the priority operational and research subject matters as identified in the TRCG annual report; and (b) provide training for enhancing Members' capability and capacity in the presentation of weather information with particular emphasis on tropical cyclone warning messages through the mass media. | Roving Seminar (with themes including media training) | nil | Provision of administrative and logistic support. | 4th | WMO/PWSP | Feedback from evaluation forms to be completed by a target audience of about 30 people. | USD 14,000 | TCTF
KRA 6 / SG 6b and 6c | 2 | To facilitate technology and knowledge transfer among TC Members through research and development initiatives. | Research Fellowship | nil | Announcement of fellowship offers and other necessary administrative support. | 3rd - 4th | TC Members | Publication of research findings in TCAR or other journals. | Fellowship offered by voluntary hosts. | TC Members
KRA 6 / SG 6b and 6c | 3 | To promote the role of women forecasters in operational tropical cyclone forecasting. | Attachment of two forecasters, preferably women, to RSMC Tokyo | nil | Facilitation of nomination process and provision of administrative support as required. | 3rd | RSMC Tokyo, WMO | Assessment as given in RSMC Tokyo report. | USD 4,500 | TCTF
KRA 4 / SG 4a, KRA 5 / SG 5b, KRA 6 / SG 6b and 6c | 4 | To facilitate TRCG coordination and planning works and to promote the understainding and use of EPS information and TIPS systems. | 1st TRCG Workshop | WGM, WGDPP | Provision of administrative and logistic support | 2nd | WMO/TCP, KMA | (a) Feedback from evaluation forms to be completed by a target audience of about 40 people; (b) TIPS software transfer to developing Members; (c) 4-year Plan of Research and Training Programme | USD 14,000 | TCTF (extra funding from KMA and WMO on top of USD 14,000 from TCTF)
Resource Mobilization Group (RMG)
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
The RMG currently has no Chair. Therefore the RMG needs a new Chair and new TORs. AWG has started to devlop projects and the RMG needs to start functioning.
Recommend RMB have representatives from each WG, AWG, WMO, ESCAP, and TCS. Recommend any Member can ask for support for a project
Advisory Working Group
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
| 1 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Participate in a focused, integrated WGM, WGH, WGDPP, and TRCG Workshop with specific deliverables defined | WGM WGH WGDPP TRCG RMG | Plan, coordinate, organize, and facilitate | ESCAP/ WMO |  | Hold an AWG meeting in conjunction with the integrated workshop to determine 2010 budget, draft AOP for 2009, and any changes required to Strategic Plan. Report results of AWG meeting to the 42nd Typhoon Committee Session.
| 2 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Analyze and evaluate work of the WGs and TRCG for effectiveness, coordination/ collaboration, and value to meet the Typhoon Committee's stated purpose | WGM WGH WGDPP TRCG RMG | Facilitate analysis and evaluation | ESCAP/ WMO |  | Review and evaluate WGs' and TRCG's proposals on behalf of the TC and make recommendations regarding the proposals.
| 3 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Provide advice/ recommendations on items requested by the TC |  | Facilitate AWG activities | ESCAP/ WMO |  | Complete advisory requests by TC within the time frame required
| 4 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Perform missions to selected Members to assist in strategic planning and grant/proposal writing |  | Facilitate planning for missions | ESCAP/ WMO |  | Complete missions and prepare and submit a report on the missions to the 41st Session of the TC.
| 5 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | To evaluate requests for addition travel to international meetings/conferences, project proposals, and other requests for additional funding, etc. |  | Facilitate | ESCAP/ WMO |  | Complete a report to be submitted to the 41st TC Session on the use of the "proactive funding" and an evaluation of the success of the proposal.
| 6 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | To fully review and make proposals to update the 2007-2011 TC Strategic Plan |  | Facilitate | ESCAP/ WMO |  | Complete a report to be submitted to the 42nd TC Session on the proposed changes and updates for the TC Starategic Plan use of the "proactive funding" and an evaluation of the success of the proposal.
| 7 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Assist in developing project proposals to be submitted for resource mobilization |  | Facilitate | ESCAP/ WMO |  | Completion and submission of at least one project proposal for funding
| 9 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Coordinate with WG in developing a strategy to develop a focus on Scientific Lectures for the 41 st Session around a theme Coping with Climate Change Within the TC Area. |  |  |  |  | At least one Scientific Lecture dealing with Climate Change for the 41 st Session