## Sheet1
APPENDIX XVII -Status on the Typhoon Committee Integrated Annual Operating Plan for Calendar Year 2008
Submitted by the Advisory Working Group - 14 January 2009
SG 1: To enhance cooperation among TC Members to reduce the number of deaths by typhoon-related disasters by half
(using the decade 1990-1999 as the base line to compare with the decade 2006-2015).
SG 2: To reduce the socio-economic impacts of typhoon-related disasters per GDP per capita by 20 per cent
(using the decade 1990-1999 as the base line to compare with the decade 2006-2015).
SG 3a: To improve the beneficial use of typhoon-related effects of typhoons by 10 per cent in water management by selected Members
(using the decade 1990-1999 as the base line to compare with the decade 2006-2015)
SG 3b: To promote increasing use of the typhoon-related beneficial effects among the Members
SG 4a: To provide reliable typhoon-related disaster information for effective policy making in risk management in various sectors.
SG 4b: To strengthen capacity of the Members in typhoon-related disaster risk management in various sectors
SG 4c: To enhance international and regional cooperation and assistance in the field of disaster risk reduction.
SG 5a: To promote and enhance culture of community-based disaster risk management among the Members
SG 5b: To promote education, training and public awareness of typhoon-related disasters among the Members
SG 6a. To strengthen RSMC capacity to respond to the needs of the Members in forecasting and capacity building
SG 6b. To improve capacity of Members to provide timely and accurate user-oriented and friendly TC products and information
SG 6c. To enhance capacity of Members' typhoon-related observation and monitoring
SG 7a: To strengthen the capacity of TCS to effectively discharge its responsibilities and functions described in the Terms
of Reference and support the Members in the implementation of the strategic goals
SG 7b: To strengthen the capacity for resources mobilization for the implementation of the strategic goals
Working Group on Meteorology
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
| 1 | To identify an appropriate Typhoon Information Processing System (TIPS) for developing Members | Develop a plan for a uniform, simple, and useful TIPS platform |  |  |  |  | (a) Complete a questionnaire on needs of the developing members (b) One Member acts as a clearinghouse for information related to TIPS (c) Analyze software for LDM | Yes |  | a. Not yet. Workshop planned for February 2009 b. No Each Member has its own TIPS, useful and simple - Will discuss during planned workshop c. No Will discuss during planned workshop
| 2 | To improve the forecasting skills throughout the Typhoon Committee region | (a) Participate in NC (b) Draft Plan for SC |  |  |  |  | (a) Successful participation in NC (b) Complete plan for SC | Yes |  | a. Yes. Korea, Japan, USA, China and others have participated b. No In process. Being organized and seeks collaborating Members
| 3 | To improve communication system in the Typhoon Committee area | Country visit to draft plan for using updated communications system |  |  |  |  | Complete Plan for using updated communications system | Yes |  | Yes. China operated an enabling system of typhoon warning dissemination and assisted five counties with VSAT in 2008. TC and WMO worked together to connect Cambodia to GTS with connection from Phnom Penh and Bangkok (The last Country in this region)
| 4 | To improve tropical cyclone classifications | Discuss methods (advantages/disadvantages) of classification systems |  |  |  |  | Agreement on a common classification system for the Typhoon Committee |  |  | Yes. Consensus can't be achieved. Do not change regional common standard. Each member establishes extra categories as necessary.
| 5 | To better assess FI change of tropical cyclones | Develop outline of database |  |  |  |  | Creation of a draft database to meet needs | Yes |  | Yes An overview report will be presented at 41st Session. China, DPRK, Japan, Philippines, ROK, Thailand and others provided their respective research on TC climate change.
| 6 | To encourage forecast discussions among Members as tropical cyclone approaches | Develop method and procedures to facilitate discussion |  |  |  |  | Develop plan and document method and procedures for Members to communicate as a tropical cyclone approaches | Yes |  | Yes, in progress. The current difficulties are language, funding , and timing. As a first step, email, phone lists, web (on-line forum), and others can be used to exchange information and for discussion among forecasters
| 7 | To improve warning information dissemination | (a) Collect and disseminate best practices. (b) HKO liaise with WMO/PWSP to explore the possibility of holding a media briefing workshop for TC Members | TRCG |  |  |  | (a) Dissemination to all Members of best practices. (b) Hold a media briefing roving seminar for TC Members |  |  | No Will be discussed during planned future workshop
| 8 | To improve flood forecasting in urban areas | Create a guideline for rainfall and storm surge forecasting in urban areas |  |  |  |  | Complete and disseminate a guideline for rainfall and storm surge forecasting in urban areas |  |  | No RSMC Tokyo is willing to provide help in setting up storm surge model in Member countries (Macao) but no publish the guideline
Working Group on Hydrology (WGH)
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 1 | Produce and use Flood Hazard Maps (FHMs) | To prepare and publish FHMs which are used by local people and municipalities for timely evacuations and planning | WGDPP | See above | (a) First (b) Second (c) Third (d) Fourth | PWRI, Japan | (a) Japan will provide technical consultation with members through help desk (b) Japan to provide its experience of legal development for FHM and some good FHM examples (c) China and Malaysia proceed already endorsed FHM projects (d) Philippines proceeds community-based FHM, (e) Thailand and Vietnam prepare FHMs at selected sites (The above FHM preparation will be done through collaboration with ex-JICA FHM trainees where ex-trainees are available.) (f) Results of above activities will be shared among TC members | (1) FHM training in PWRI, Japan (2) Local costs in members to prepare FHMs | (1) JICA (2) Members' own funds | a. Yes b. Yes c. Yes d. Yes e. Yes f. No, but meeting on this and will finalize in 2009
KRA 1 SG1 | 2 | Establish debris flow and landslides warning system | Establish methodologies in TC region of using Critical Lines (CLs) for issuing evacuation orders/advices to communities against sediment-related disasters | WGDPP | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) Through THD, Japan will actively provide technical consultation with interested members for setting CLs (b) All interested members will set CLs at model sites (c) Japan to study how to apply CLs for locations where past data are scarce and provide results to members |  |  | a. Yes through a help desk b. Yes c. No Under preparation
KRA 1 SG 1 KRA 2 SG 2 KRA 3 SG 3a | 3 | To optimize reservoir operations | Develop and implement guidelines for optimal reservoir operations |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) ROK provides general and technical reservoir operation Guidelines to members by the end 2007 (if there is a need to settle stakeholder indolent issue in general GL, this to be done by middle 2008) (b) ROK will publish in CD Rom on the final dam operation GLs (c) As Follow-up process, ROK provides consultation to members on specific dam operation cases when requested |  |  | a. Yes. Draft completed and circulated b. Yes. Guideline published by 41st annual session c. Yes ROK is ready to provide consultations
KRA 1 SG 1 KRA 2 SG 2 | 4 | To improve flood forecasting capability and accuracy by improving model guidance and use of the guidance | Identify and evaluate available flood forecasting models using developed guidelines on model development, calibration, verification, evaluation, and comparison. |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) ROK will provide revised MOFFS methodology and users manual by end 2007 (b) As follow-up process, ROK will open discussion by middle 2008 for members to apply the proposed model evaluation system (c ) ROK publishes CD Rom on the final revised MOFFS as soon as discussion is finished |  |  | a. Yes b. Yes c. Yes The results will very soon be put on the web so can help implement in other TC Members' areas and outside of the TC.
KRA 1 SG 1 KRA 2 SG 2 | 5 | To improve flood forecasting capability and accuracy through On-the-Job Training (OJT) | Conduct OJT on flood forecasting through the use of models, observations, and past events |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) Malaysia conduct FF OJT inviting 2 members in Jan. 2008 that will be recorded as 2007 carry-over activity) For activities in 2008, (b) Selected members prepare relevant hydrological and catchments data/information for selected pilot areas (c) Malaysia reviews data and information on selected pilot areas (d) Malaysia conducts 3 week OJT for 2 Members in late 2008 | TCTF 3,000 USD to support intl. participants, and local funds to be prepared by Malaysia | TCTF | a. Yes b. Yes c. Yes d. Yes Discussed how to increase the impact, active preparation, past experience. Also looked at International Training Course on Operational Flood Forecasting System and its Application (OFFSA)
KRA 1 SG 1 KRA 2 SG 2 | 6 | To improve flood forecasting capability and accuracy through use of a flood forecasting system. | Development and publication of guidelines for the establishment of a flood forecasting system. |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) By end 2007, China will prepare and submit a report on 2007 FF international training, together with developed FF guidelines and training texts in CD-Rom style) As follow-up process, (b) China will make technical consultations to members if any, (c) China will contribute to enriching OJT in Malaysia in 2008 | Funding will be needed for this training. | TCTF | a. Yes. Materials available but need to upload them on TC web site b. Yes c. Yes
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4b KRA 5 SG 5a | 7 | To improve flood forecasting capability and accuracy through use of a community-based flood forecasting and warning system (CBFFWS) | Development and publication of guidelines on a community-based approach for a flood forecasting and warning system |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | By end 2007, Philippines compiles its experiences of CBFFWS in CD-Rom and provide to members for application. In 2008 as follow-up process, Philippines will give advices to members if any requested |  |  | Yes. Final guideline published by the 41st annual session.
KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4b KRA 5 SG 5a | 8 | To improve hydrological products to meet the requirements of users | Produce, collect, compile, and publish examples of user friendly hydrological products |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | By end 2007, Philippines collects user friendly info from members and compile them in CD-Rom together with Philippines examples. In 2008 as follow-up process, TCS, with advices from Philippines, will try to collect more user-friendly info from members and upgrade the contents |  |  | Yes. Philippines collected data. In the process of following up to collect additional information.
KRA 1 SG 1 KRA 2 SG 2 | 9 | To improve management of floods and other typhoon-related disasters in urban areas. | Compilation of experiences among the Members; Survey of emerging issues in the Committee Area; Preparation of detailed programme for enhanced cooperation among the Members, including preparation of guidelines | WGM WGH WGDPP TRCG AWG RMG | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) small WS will be held inviting all 3 WGs to map out detailed idea of the project - venue to be fixed (b) Interested members will be invited to tackle the relevant issues based on the WS discussion - China MWR will be invited to coordinate the activities | TCTF for the support of participating small WS |  | a. Yes in December 2008 b. No In progress, after the small WG meeting.
KRA 1 SG 1 KRA 2 SG 2 | 10 | To improve decision making on priorities of investment on infrastructure projects for disaster prevention | To develop common procedures and tools for assessment of socio-economic impact of typhoon-related disasters for an effective decision making on investment of infrastructure on the basis of the UNESCAP Disaster Impact Calculator | WGDPP | See above | Detailed concept by second quarter; workshop on project implementation by third quarter; selection of pilot countries in fourth quarter |  | Acceptance of ROK to fund the project in 2008 and acceptance of TC Members to participate in project | Funding expected from ROK | ROK and participating TC Members | Yes 5-year project plan developed. Requested relevant information from each Member.
Working Group on Disaster Prevention and Preparedness (WG DPP)
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
KRA 4 SG 4b and 4c KRA 5 SG 5b | 1 | Promote value of TC DIS to TC Members | Send 2 to 3 experts on missions to explain the purpose and use of the TC DIS and to promote its benefits |  | Assist in planning the expert missions | First or Second | ADRC, ISDR, etc. | Complete expert missions to at least 2 developing members of the Typhoon Committee to facilitate implementation of the TCDIS in the respective Member | US $12,000 | NEMA, Korea TCTF | Exceeded goal. Completed 4 missions.
KRA 4 SG 4b and 4c KRA 5 SG 5b | 2 | Enhance TCDIS and establish methodology to assess the socio-economic impacts of disasters | Conduct the 3rd Meeting of WGDPP to brief Members on TCDIS and discuss on assessment of the social and economic impacts of natural disasters | WGM WGH | Plan, coordinate, organize and facilitate | Second | ADRC, ISDR, etc. | Brief Members on how to provide input and maintain TCDIS as well as its potential applications and discuss on assessment of the social and economic impacts of natural disasters | US $30,000 | NEMA, Korea and TCTF | Yes, developing web based system.
KRA 4 SG 4b and 4c KRA 5 SG 5b | 3 | Operational implementation of TCDIS | Maintain Hardware, Software of TCDIS System and upgrade disaster information and other contents by inputs from Members | WGM WGH | Assist in collecting necessary data from Members | Expect to go operational by November 2008 | ADRC, ISDR, etc. | Complete each Member's disaster information in 2008 | US $30,000 for maintenance | NEMA, Korea and TCTF | Yes, except for 2 Members.
KRA All SG ALL | 4 | Review progress of TC DIS project and enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Participate in a focused, integrated WGM, WGH, WGDPP, TRCG, and AWG Workshop with specific deliverables defined and to review progress of TC DIS project and future activities of WGDPP | WGM WGH WGDPP TRCG AWG RMG | Plan, coordinate, organize, and facilitate | Second or third |  | Discuss future activities of WGDPP, report on TCDIS and collaboration with other WGs |  |  | Yes
KRA 4 SG 4b and 4c KRA 5 SG 5b | 5 | Launch TCDIS | Make presentation on WGDPP's Activities in 2008 |  | Assist in including presentation on the TC Session agenda | Fourth |  | Publicity event on official launch of TCDIS; Present WGDPP's Activities in 2008 and operation plans in 2009 |  |  | Yes with support by ADRC. Phase II is planned to make this web based and Phase II will be to coordinate with Members on this. TCDIS willl serve as a foundation to support other activitiies and for Decision Support System
KRA 4 SG4b and 4c KRA 5 SG 5b | 6 | To develop a conceptual framework consistent with Multi-Hazard Early Warning System in conjunction with other WGs to make a link with TCDIS | Prepare a concept and proposal on program of action | WGM, WGH, TRCG, AWG | Assist in collecting inputs from Members | Concept paper by first quarter and initiate public education activities jointly with mission |  | Acceptance of concept paper and mission |  |  | No MC Wong is developing concept paper as a designated as a member of WMO Expert team.
Training and Research Coordinating Group (TRCG)
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
KRA 6 SG6b and 6c | 1 | To: (a) enhance Members' capability and capacity in the priority operational and research subject matters as identified in the TRCG annual report; and (b) provide training for enhancing Members' capability and capacity in the presentation of weather information with particular emphasis on tropical cyclone warning messages through the mass media. | Roving Seminar (with themes including media training) |  | Provision of administrative and logistic support. | 3rd or 4th | WMO/PWSP | Feedback from evaluation forms to be completed by a target audience of about 30 people. | USD 20,000 | TCTF | No. Postponed.
KRA 6 SG 6b and 6c | 2 | To facilitate technology and knowledge transfer among TC Members through research and development initiatives in tropical cyclone forecasting. | Research Fellowship |  | Announcement of fellowship offers and other necessary administrative support. | 2nd - 4th | TC Members | Publication of research findings in TCAR or other journals. | Funding offer from participating hosts on a voluntary basis | TC Members | Yes
KRA 6 SG6b and 6c | 3 | To promote the role of women forecasters in operational tropical cyclone forecasting. | Attachment of two women forecasters to RSMC Tokyo |  | Facilitation of nomination process and provision of administrative support as required. | 3rd | RSMC Tokyo, WMO | Assessment as given in RSMC Tokyo report. | USD 5,000 | TCTF | Yes. Need to conduct an assessment of this training.
KRA 6 SG6b and 6c | 4 | To provide on the web, training materials and research results in connection with TRCG activities for reference by Members. | Collating readily available references material and posting them onto a dedicated web page managed by TRCG onto the TCS web site. |  | Making ready the TCS web site for hosting reference material | 2nd |  | Upload of information within one month after the reference is ready and available |  |  | Yes Knowledge based web portal of TC TCS web site. Prototype looks very good.
Resource Mobilization Group (RMG)
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
| 1 | To identify sources/ideas of funding to meet TC mission | Contact ESCAP and WMO for ideas/sources of possible funding |  |  |  | ESCAP WMO | Develop a list of ideas/sources of possible funding and contact information |  |  | No
| 2 | To create a database with Members specific criteria | Contact Members and request resource mobilization information for data base |  | Send Letter |  |  | Creation of an initial resource mobilization database |  |  | No
| 3 | To conduct resource mobilization pilot projects | Identify projects for pilot program |  |  |  |  | Submit one complete pilot resource mobilization request to donor organization |  |  | No
| 4 | To establish a systematic strategy on resource mobilization | To mobilize participation of key stakeholders in the formulation of a strategy for RMG for TC |  | To facilitate participation |  |  | Accceptance of a strategy by TC |  |  | No
The RMG currently has no Chair. Therefore the RMG needs a new Chair and new TORs. AWG has started to devlop projects and the RMG needs to start functioning.
Recommend RMB have representatives from each WG, AWG, WMO, ESCAP, and TCS. Recommend any Member can ask for support for a project
Advisory Working Group
SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed - Yes or No
| 1 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Participate in a focused, integrated WGM, WGH, WGDPP, and TRCG Workshop with specific deliverables defined | WGM WGH WGDPP TRCG RMG | Plan, coordinate, organize, and facilitate | ESCAP/ WMO |  | Hold an AWG meeting in conjunction with the integrated workshop to determine 2009 budget, draft AOP for 2009, and any changes required to Strategic Plan. Report results of AWG meeting to the 41st Typhoon Committee Session. |  |  | Yes
| 2 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Analyze and evaluate work of the WGs and TRCG for effectiveness, coordination/ collaboration, and value to meet the Typhoon Committee's stated purpose | WGM WGH WGDPP TRCG RMG | Facilitate analysis and evaluation | ESCAP/ WMO |  | Review and evaluate WGs' and TRCG's proposals on behalf of the TC and make recommendations regarding the proposals. |  |  | Yes
| 3 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Provide advice/ recommendations on items requested by the TC |  | Facilitate AWG activities | ESCAP/ WMO |  | Complete advisory requests by TC within the time frame required |  |  | Yes
| 4 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Perform missions to selected Members to assist in strategic planning and grant/proposal writing |  | Facilitate planning for missions | ESCAP/ WMO |  | Complete missions and prepare and submit a report on the missions to the 41st Session of the TC. |  |  | 1 mission completed
| 5 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | To evaluate requests for addition travel to international meetings/conferences, project proposals, and other requests for additional funding, etc. |  | Facilitate | ESCAP/ WMO |  | Complete a report to be submitted to the 41st TC Session on the use of the "proactive funding" and an evaluation of the success of the proposal. |  |  | Partially. AWG did support the small meeting of WGs. However, AWG needs to become more active in this area.
| 6 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Create a 1 to 2 page brochure outlining the TC Vision, Mission, KRAs, and SGs |  | Facilitate | ESCAP/ WMO |  | Completion of a 1 to 2 page brochure outlining the TC Vision, Mission, KRAs, and SGs |  |  | Yes
| 7 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Assist in developing project proposals to be submitted for resource mobilization |  | Facilitate | ESCAP/ WMO |  | Completion and submission of at least one project proposal for funding |  |  | Yes. Conduct a small meeting of WGs and developed framework of a proposal.
| 8 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Proposed new emblem/symbol and song for the Typhoon Committee in celebration of 40th Anniversary. Member-wide contest – similar to Hong Kong’s Name, but all 14 Members participating Increase publicity and recognition |  | Facilitate | ESCAP / WMO |  | Present a proposed emblem and song to the 41st Session to consider |  |  | Yes
| 9 | To enhance the Typhoon Committee's effectiveness and efficiency in meeting its purpose stated in the Statute of the Typhoon Committee | Coordinate with WG in developing a strategy to develop a focus on Scientific Lectures for the 41 st Session around a theme Coping with Climate Change Within the TC Area. |  |  |  |  | At least one Scientific Lecture dealing with Climate Change for the 41 st Session |  |  | Yes