APPENDIX XVIII

Working Group on Meteorology (WGM) – AOP 2012 Implementation Status

| SP’s KRA and SG | Objective Number | Objective | Action | Other WG’s involved | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Coordinator | Completed – Yes or No |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 1 KRA 2 KRA 4 | 1 | Assessment report on the impact of climate change on tropical cyclone in TC region | - Publish the "2ndassessment report on the impact of climate change on tropical cyclone track and impact area in TC region" - Follow-up of the recommendation of the best-track consolidation meeting | WGDRR | (a) 3rd (b) 4th | HKO/China, CMA, USA, JMA, KMA, Macao/China (coordinator) and Members | (a) Publish the 2nd report in 45th Session; (b) Consolidate the operational procedures of tropical cyclone analysis for inclusion in the TOM, exchange and compare the historical best-tack datasets, including CI numbers if available, among the centers | US $2,500 (for publication of the 2nd report) | TCTF | (a) Tam Iu Man/Leong Weng Kun (Macau, China) (b) Masashi Kunitsugu (JMA) | (a) Yes (b) Yes |
| KRA 1 KRA 2 KRA 4 /SG4(a) | 2 | Storm surge watch scheme for UFRM | - To conduct training of storm surge model for UFRM during the annual TC attachment training by RSMC Tokyo - To provide storm surge time series charts at one point upon TC Member’s request - To develop storm surge time series charts at more than one point if so requested by Members | WGH WGDRR TRCG | (a) 3rd (b-c) 4th | JMA | (a) Conduct of training and subsequent evaluation (b) Provide storm surge time series charts at one point upon TC Member’s request (c) Develop storm surge time series charts at more than one point if so requested by Members | / | / | Masashi Kunitsugu (JMA) | (a) Yes (b) Yes (c) Yes |
| KRA 1 KRA 2 KRA 6 / SG 6b and 6c | 3 | Transfer of the Typhoon Information Processing System technology | - To improve the English version of KMA’s typhoon information processing system (TAPS) - To train the meteorologists and forecasters of TC Members on TAPS from May with the duration of 2 months | TRCG | 2nd - 4th | KMA, Viet Nam, Members | Submission of report on the technique and training of TAPS | US $2000 | TCTF | Mr. Ki-Ho Chang (KMA) | (a) Yes (b) Yes |
| KRA 1 KRA 2 KRA 6 /SG 6b and 6c | 4 | Enhanced use of ensemble forecast | (a) To get feedback from Members for improvement of the TCEFP website through WMO’s questionnaire (b) To promote Members’ understanding of EPS through SWFDP and its training workshop | WGDRR TRCG | 2nd- 4th | JMA,CMA, HKO/China, Viet Nam, KMA and WMO | Improvement of the web site will be implemented and will be reported in the Progress report | / | / | Masashi Kunitsugu (JMA) | (a)Yes (b) No (postponed) |
| KRA 6 / SG 6b and SG 6c | 5 | Web-based typhoon forum | - Expand the number of registered users and the team of moderators on related topics - To upgrade the on-line forum by sharing more real-time observation, forecast and warning information by Members | AWG, WGH WGDRR | 1st- 4th | CMA RSMC Tokyo, JTWC, Members | Effective use of web-based typhoon forum as shown by website access statistics | / | / | Li qingqing (CMA) | (a) Yes (b) Yes |
| KRA1 KRA2 KRA6 /SG6b and 6c | 6 | Development of regional radar network | - Specialized attachment training for TMD radar staff upon submission of the progress report of the operating status of the TMD radar system by TMD - To follow-up the recommendations and the suggested roadmap of the expert team and to develop the radar composite map which covers the area of the UFRM pilot city in Thailand as the first step | TRCG | 4th | TMD, JMA | Submission of the progress report, including a detailed schedule for the establishment of the radar composite map | US $3000 | TCTF | Masashi Kunitsugu (JMA) Derek Leong (TCS) PatcharaPetvirojchai (TMD) | (a) Yes (b) Yes |
| KRA1 KRA2 KRA6 / SG 6b and 6c | 7 | Verification of tropical cyclone operational forecast | - Organize a training workshop on typhoon landfall forecast demonstration project - Modify the methods to verify the generation, track and intensity forecast accuracy of tropical cyclones in the Asian-Pacific Region - Assess the performance of objective model prediction and the official forecast of Members. | TRCG | (a-b) 2nd (c) 4th | CMA, RSMC Tokyo, JTWC, Members, WMO | (a) Hold a training workshop and subsequent evaluation of the training (b) Submit report of the assessment of the performance of objective model prediction and the official forecast of Members in 45th Session | US$3,000 | TCTF | Yu Hui (CMA) | (a) Yes (b) Yes |
|  | 8 | Publication of Tropical Cyclone Research and Review | - Improvement of the editorial procedure (include visit the visiting editor) - Publish the journal quarterly | AWG, WGH, WGDRR, TRCG | 1st- 4th | CMA, TCS Members | Progress report | US$3,000 | TCTF | Zhou Xiao (CMA) | (a) Yes (b) Yes |
| KRA1 KRA2 KRA4 / SG4a | 9 | QPE/QPF for UFRM | - To conduct a forum and training for UFRM pilot cities - To provide QPE/QPF training to TC Members participating in the UFRM pilot projects upon a request - To conduct training on QPE/QPF during the annual TC attachment training at RSMC Tokyo - Upon availability of budget, QPE/QPF Workshop to be held by MMD | WGH WGDRR TRCG | (a) 4th (b) 1st - 4th (c) 3rd | RSMC Tokyo HKO, CMA | Conduct of training and subsequent evaluation of the training | US$5,000 | TCTF | Masashi Kunitsugu (JMA) | (a) No (b) Yes (c) Yes (d) No (due to budget constraint) |
| KRA1 KRA2 KRA6 | 10 | South China Sea typhoon forecast | - Further improvement of TRAMS model - Provide more products relate to typhoon assess through website - Establish the feedback column for all Members |  |  | CMA, Viet Nam, PAGASA, MMD | Submission of the report on the assessment of model and website | / | / | Zhang Zhongcheng (CMA) | (a) Yes (b) Yes (c) Yes |
| KRA1 KRA2 KRA6 | 11 | Development of web-based typhoon seasonal prediction system | - Development of web portal for typhoon seasonal prediction - Providing typhoon seasonal prediction results to members through web-based portal page together with the participating members’ results |  |  | KMA, CMA Members | Submission of the report on assessment of seasonal prediction models | / | / | Sangwook Park (KMA) | (a) Yes (b) Yes |
| KRA1 KRA2 KRA6 | 12 | Improvement of severe weather forecasting and interaction with user communities | Development of collaborative relationship with WMO severe weather forecast demonstration project | WGH, WGDRR, TRCG | 2-4 | Viet Nam, Cambodia, Lao, Thailand, WMO | Progress report | / | / | NHMS of Viet Nam | Yes |

WORKING GROUP on HYDROLOGY (WGH) - AOP 2012Implementation Status

| SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed – Yes or No |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 1 | Projects on Urban Flood Risk Management in TC Region | a)Initiate developing OSUFFIM in case the STDF of Macao, China approved the proposal; b)case Study on QPE/PQF Application in UFRM in cooperation with WGM; c)Continue to conduct case Study on SSWS Application in UFRM; d)Continue to conduct pilot study in Pilot cities; e)Drafting UFRM Guidelines | WGM WGDRR | coordination | (a) First (b) Second (c) Third (d) Fourth | ESCAP WMO | (a-1) compile the first draft and send to all drafting members ASAP, but not later than Jan. 1, 2012; (a-2)UFRM guidelines drafting meeting was proposed to be held in WMO Nanjing RTC (a-3) UFRM Workshop, funded by ESCAP (b-1)Fund application from Macao STDF (b-2)initiate developing OSUFFIM (c-1)start the case study on QPE/QPF application in UFRM, in cooperation with WGM (c-2)start the case study on SSWS application in UFRM (c-3)continue the pilot study in pilot cities (c-4)training for pilot city Members (d-1)second version of UFRM guidelines at IWS (d-2)pilot study report from related Members (d-3)finalizing the Guidelines at 45th Session. | (a) TCTF 10000USD for TF/PC activities (b)Funding from STDF of Macao, China | potential ESCAP, WMO, ADB, JICA, KOICA, Macao STDF; etc | (a-1) YES (a-2) YES (a-3) YES (b-1) YES (b-2) YES (c-1) YES (c-2) YES (c-3) YES (c-4) YES (d-1) YES (d-2) YES (d-3) YES |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 6b | 2 | Assessment System of Flood Control Measures on Socio-economic Impacts | Apply ASFCM system in TC members who want to participate in to evaluate and enhance system capability |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a,b,c,d)Drafting ASFCM User’s manual (a,b,c,d)Apply and assess the information provided from TC members to consult the effect of the measures |  | MLTM | (a,b,c,d) ongoing |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 3 | Project on Hazard Mapping for sediment-related disasters | To raise local people’s and local government's awareness for sediment-related disasters. To separate people and their properties from high-risk areas to reduce their damages by disasters | WGDRR | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a,b,c,d) guide Members countries to make Hazard map. (b) Find requirement from TC Members. (d) Workshop to solve the Member's issues at next IWS (d) Drafting the guideline to reduce damage of sediment-related disaster and to spread Japanese technique in Typhoon Committee Region. | TCTF (1)2000USD for publishing the guideline; | TCTF NILIM SABO | (a,b,c,d) YES (b)Cancelled (d)Cancelled (d) YES |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5b | 4 | Project on development and application of flood disaster preparedness indices |  | WGDRR | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a-1) establish evaluation equation (a-2)conduct direct FDPI survey and feedback analyzed results to Marikina city(Philippines), UbonRachathani(Thailand), and Hat Yai(Thailand) (b)create multi-language FDPI and FDPI automatic self -evaluation system on the website (c)collect and compile the information for feedback to TC members (d)drafting and printing the final report | TCTF 2000USDforPrinting final report | ICHARM | (a-1)YES (a-2) YES (b)Soon (c) Soon (d) Soon |
| RA1, SG1 KRA2, SG2 KRA4 SG 4a, KRA5, SG 5b | 5 | Project on the utilization of Satellite-based information for Typhoon-related disaster management |  | WGM, WGDRR, TRCG | See above | (a) First (b) Second (c) Third (d) Fourth | ESCAP, JAXA, ICHARM | (a) Operational Sentinel Asia and Urban Flood Training for TC, PTC & Pacific membersfrom 27th Feb – 2nd March 2012 in Macao, China. (b-d) to conduct case study and good practice of image product of various satellites | Funds for inviting participants, lecturers and other WS organization cost | ESCAP, JAXA, ICHARM | - YES (b-d)YES |
| KRA1 KRA 4 SG 4a SG 4bKRA5 SG 5a KRA 7 SG 7b | 6 | Development of comprehensive counterplan for extra-ordinary flood | Develop comprehensive counterplan for extra-ordinary flood by investigation and analysis of historical flood damage | WGDRR WGM | See above | - First - Second - Third - Fourth | RID of Thailand, PAGASA of Philippines | (a) Understand TC members’ causes and effect of extra-ordinary flood damage including dam operation. (b-1)Survey and data collection of selected TC members (Thailand and Philippines) about external forces caused historical flood (b-2)workshop (c)Investigate selected TC members’ flood control capacity considering geological and social conditions (d)Analyze selected TC members’ flood control guidance and management system | TCTF 4,000USD for survey and data collection | MLTM (KICT, K-water) TCTF | (a) YES (b-1)YES (b-2)YES (c)ongoing (d)ongoing |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 6b | 7 | Project on estimation for socio-economic impact of sediment-related disaster | to improve former projects with establish common collecting format and methods of investigation for disasters to estimate estimation for socio-economic impact of sediment-related disaster and to share common technical background in TC members. | WGDRR | See above | (a)First (b)Second (c)Third (d)Fourth |  | (a) Submit tentative format and methods of investigation from Japan for TC members. (b) Collecting the idea to improve tentative format and make trial version. |  | NILIM SABO | (a) YES (b) YES |

SG1:  To enhance cooperation among TC Members to reduce the number of deaths by typhoon-related disasters by half in the ten years of 2006 – 2015 (using the ten years of 1990 - 1999 as the base line).

SG2:  To reduce the socio-economic impacts of typhoon-related disasters per GDP per capita by 20 per cent in the ten years of 2006- 2015 (using the ten years of 1990 - 1999 as the base line).

SG 3a:  To identify and explore the beneficial use of resources such as rainfall brought by typhoon.

SG 3b:  To study and promote the increasing use of typhoon-related beneficial effects among the Members.

SG 4a:  To provide reliable typhoon-related disaster information for effective decision making in risk management in various sectors.

SG 4b:  To strengthen capacity of the Members in typhoon-related disaster risk management in various sectors.

SG 4c:  To enhance international and regional cooperation and assistance in the field of disaster risk reduction.

SG 5a:  To promote and enhance culture of community-based disaster risk management among the Members.

SG 5b:  To promote education, training and public awareness of typhoon-related disasters among the Members.

SG 6a:  To facilitate RSMC capability to respond to the needs of the Members in forecasting and capacity building.

SG 6b:  To improve capacity of Members to provide timely and accurate user-oriented and friendly tropical cyclone products and information.

SG 6c:  To enhance capacity of Members' typhoon-related observation, monitoring, forecasting and warning.

SG 7a:  To strengthen the capacity of Typhoon Committee to effectively discharge its responsibilities and functions described in this Strategic Plan and completed its stated mission     in accordance with the Typhoon Committee’s Statute.

SG 7b:  To mobilize available resources and engage collaborators for the implementation of the strategic goals.

KRA 1:  Reduced Loss of Life from Typhoon-related Disasters.

KRA 2:  Minimized Typhoon-related Social and Economic Impacts.

KRA 3:  Enhanced beneficial typhoon-related effects for the betterment of quality of life.

KRA 4:  Improved Typhoon-related Disaster Risk Management in Various Sectors.

KRA 5:  Strengthened Resilience of Communities to Typhoon-related Disaster.

KRA 6:  Improved capacity to generate and provide accurate, timely and understandable information on typhoon-related threats.

KRA 7:  Enhanced Typhoon Committee’s Effectiveness, Efficiency and International Collaboration.

WORKING GROUP on DISASTER RISK REDUCTION (WGDRR) - AOP 2012

| SPs KRA and SGs | Objective Number | Objective | Action | Other WG’s involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed Yes or No |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 1 | Transferring the WGTCDIS | (i) Extend the WEB GIS based Typhoon Committee Disaster Information System (WGTCDIS) for early warning system and localized assessing in conjunction with other WGs (ii) Perform the expert mission on the WGTCDIS for Philippines and USA on March, 2011 | TCS WGM WGH | Assist in planning the expert mission | First | WMO UNESCAP ADRC UNISDR | (i) Complete collecting disaster information from Thailand, Philippines, USA and Cambodia (ii) Send expert team for implementation of the WGTCDIS to two Members of Philippines and USA | US $12,000 | NDMI, Korea and TCTF | (i) Yes (ii) Yes |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 2 | Enhancing the WGTCDIS | (i) Develop Geo-Linking system for integrated disaster risk assessment (ii) Develop GIS based information sharing system to collect and disseminate various disaster related information | WGM WGH | Provide guideline to support $1000 for collecting disaster information | Fourth | ADRC UN/ISDR | (i) Complete developing the Geo-Linking system (ii) Complete developing the GIS based information sharing system | US $ 36,000 | NDMI, Korea and TCS | (i) Yes (ii) Yes |
| KRA ALL SG ALL | 3 | Providing WGTCDIS for UFRM Project | (i) Provide WGTCDIS training in a focused, integrated WGM, WGH, TRCG Workshop (ii) Review progress of WGTCDIS project for UFRM and future activities of WGDRR (iii) Produce localized disaster risk maps for TC Members | WGM WGH TRCG AWG RMG | Provision of administrative support | Second or Third |  | (i) Complete report on Urban Flood Risk Management (UFRM) Project |  |  | On going |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 4 | Modifying the WGTCDIS | (i) Calibrate and validate the WGTCDIS for all typhoons in 2012 with TC Members (ii) Modify the estimation methods to adapt WGTCDIS on TC Members. |  | Assist in including presentation on the TC Session agenda | Fourth |  | (i) Successful acceptance of WGTCDIS by TC Members |  |  | (i) Yes |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 5 | Publishing the annual disaster assessment report | (i) Collect disaster information from TC Members (ii) Held annual WGDRR Workshop (iii) Assess typhoon related disasters in the TC Region (iv) Establish the standard disaster information database | WGM WGH TRCG AWG | Assist in collecting disaster information from Members | Fourth |  | (i) Publish the annual disaster assessment report (ii) Hold WGDRR workshop | US $ 3,000 |  | (i) No (ii) Yes |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 6 | Emergency response network for urban risk management | (i) Develop the urban disaster risk assessment system based on risk maps (ii) Develop the dissemination system to share situation information to escape from dangerous area or reduce traffic jam (iii) Provide guideline to manage disasters in urban area, educate and train earlier disaster | AWG WGH TRCG | Provision of administrative support | Fourth | WMO UNESCAP ADRC UNISDR Columbia University | (i) Develop the urban disaster risk assessment system |  |  | On going |
| KRA 4 SG 4b and 4c KRA 5 SG 5b | 7 | A feasibility study on the real-time transmission of severe weather warning and carry out trials | (i) Assist in liaison work for implementation commenced (ii) Extend dissemination of warnings to become available on SWIC (Severe Weather Information Center) by the 44th Session | WGM TRCG | Assist in liaising with focal points | Fourth | WMO | (i) Complete trial dissemination of weather warnings (ii) Extend dissemination of warnings to a few more members |  |  | (i) Yes (ii) Yes |
| KRA 4 SG 4b and 4c KRA 5 SG 5b | 8 | A pilot project of community weather stations in TC Members | (i) Raise public awareness on climate change (ii) Offer an expert of Hong Kong, China for visiting Vietnam to implement the community weather station | WGMWGH | Assist in liaising with focal points | Fourth | ESCAP | (i) Weather station installed in two interested TC member | US $4,000 | TCTF | (i) Yes |

SG 1:	To enhance cooperation among TC Members to reduce the number of deaths by typhoon-related disasters by half (using the decade 1990-1999 as the base line to compare with the decade 2006-2015).

SG 2:	To reduce the socio-economic impacts of typhoon-related disasters per GDP per capita by 20 per cent (using the decade 1990-1999 as the base line to compare with the decade 2006-2015).

SG 3a:	To improve the beneficial use of typhoon-related effects of typhoons by 10 per cent in water management by selected Members (using the decade 1990-1999 as the base line to compare with the decade 2006-2015)

SG 3b: 	To promote increasing use of the typhoon-related beneficial effects among the Members

SG 4a:	To provide reliable typhoon-related disaster information for effective policy making in risk management in various sectors.

SG 4b:	To strengthen capacity of the Members in typhoon-related disaster risk management in various sectors

SG 4c:	To enhance international and regional cooperation and assistance in the field of disaster risk reduction.

SG 5a: 	To promote and enhance culture of community-based disaster risk management among the Members

SG 5b: 	To promote education, training and public awareness of typhoon-related disasters among the Members

SG 6a:	To strengthen RSMC capacity to respond to the needs of the Members in forecasting and capacity building

SG 6b: 	To improve capacity of Members to provide timely and accurate user-oriented and friendly TC products and information

SG 6c: 	To enhance capacity of Members' typhoon-related observation and monitoring

SG 7a:  To strengthen the capacity of TCS to effectively discharge its responsibilities and functions described in the Terms of Reference and support the Members in the implementation of the strategic goals

SG 7b:  To strengthen the capacity for resources mobilization for the implementation of the strategic goals

KRA 1:  Reduced Loss of Life from Typhoon-related Disasters.

KRA 2:  Minimized Typhoon-related Social and Economic Impacts.

KRA 3:  Enhanced beneficial typhoon-related effects for the betterment of quality of life.

KRA 4:  Improved Typhoon-related Disaster Risk Management in Various Sectors.

KRA 5:  Strengthened Resilience of Communities to Typhoon-related Disaster.

KRA 6:  Improved capacity to generate and provide accurate, timely and understandable information on typhoon-related threats.

KRA 7:  Enhanced Typhoon Committee’s Effectiveness and International Collaboration.