APPENDIX XIX

Working Group on Meteorology (WGM) – Annual operating projects (AOPs) 2013

| SP’s KRA and SG | Objective Number | Objective | Action | Other WG’s involved | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Coordinator |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 1 KRA 2 KRA 4 | 1 | Contribution to SSOP | - To collect current status of Members’ SOP for multi-hazard early warning (MEW) for coastal region - To convey the above outcomes to SSOP project for the implementation of SSOP | WGH WGDRR TRCG | 1st -4th | TCS, Members, ESCAP WMO PTC ADRC | - Report of the collection of current status of Members’ SOP for MEW for coastal region | TBD | SSOP Budget | Renito Paciente (PAGASA) |
| KRA 1 KRA 2 KRA 6 /SG 6b and 6c | 2 | Enhanced use of ensemble forecast | - To get feedback from Members for improvement of the TCEFP through WMO’s questionnaire and SWFDP in Southeast Asia - To investigate tropical cyclogenesis prediction in the western North Pacific on medium-range timescales using the TIGGE data and on intraseasonal timescales using the JMA 1-month EPS conjunction with WMO-TCEFP | / | 1st -4th | JMA | (a) Improvement of the web site responding to the feedback considering the provided data and feedback from SWFDP, if available (b) Investigate the TC genesis prediction over the western North Pacific during the 2009 and 2010 seasons using the TIGGE and JMA EPS data, and report the results | / | / | Masashi Kunitsugu (JMA) |
| KRA1 KRA2 KRA6 / SG 6b and 6c | 3 | Verification of tropical cyclone operational forecast | - To carry out post-season verification and reliability analyses on the operational forecast of tropical cyclones in Committee session - To further improve the evaluation system for tropical cyclone forecast, with special attention on genesis forecast conjunction with WMO-TLFDP (to be included in the TC Fellowship Scheme) - To offer fellowship for training on (b) | AWG, TRCG | 1st -4th | CMA, KMA, HKO, RSMC Tokyo, Members | (a) Submission of the post-season verification report (b) Progress report on the improvement of evaluation system for tropical cyclone forecast | US$5,000 | TCTF | Ms. Yu Hui (STI/CMA) |
| KRA1 KRA2 KRA6 | 4 | Improvement of South China Sea typhoon forecast | - Further improvement of TRAMS model - Provide more products relate to typhoon assess through website | / | 1st -4th | CMA, Viet Nam, PAGASA, MMD | Submission of the report on the assessment of model and website | / | / | Chen Zitong (CMA) |
| KRA1 KRA2 KRA6 | 5 | Development of typhoon seasonal prediction system | - To further develop the techniques of typhoon seasonal prediction - To establish the semi-operational web-based portal to provide the products of typhoon seasonal prediction for TC Members | / | 1st -4th | KMA Members | Submission of the report on assessment of seasonal prediction models | / | / | Sangwook Park (KMA) |
| KRA1 KRA2 KRA6 | 6 | Improvement of severe weather forecasting and interaction with user communities | - Semi-operation of SWFDP-SeA portal webpage - Provide more products in real time such as Daily Severe Weather Forecasting Guidance, thunderstorm index forecasting map, AMV, ASCAT, tropical cyclone track and intensity forecast, nowcasting for rainfall and storm, and Medium Weather Guidance - Investigate interpretation of EPS products as well as its NWP guidance - coordinate real-time 24/7 communications among the participating centres in the region of the project (to maintain a list of 24/7 contact information; telephone, fax, e-mail) | WGH, WGDRR, TRCG | 2nd-4th | Viet Nam, Cambodia, Lao, Thailand, WMO | Progress report | / | / | Vo Van HOA NHMS of Viet Nam |
| KRA1 KRA2 KRA6 /SG6b and 6c | 7 | Development of regional radar network | - Development of source codes for conversion from UF format to GRIB2 format, as well as ones for production of EILS with the technical support from JMA - Specialized attachment training for TMD radar staff or an expert mission to TMD to complete the action (a) upon receipt of the progress report from TMD - To make the preparation studies on developing the composite map for the coverage of Thailand as well as utilizing QPE techniques by TMD | TRCG | (a) 4th (b) 4th (c) 4th | TMD, JMA | Submission of the progress report, including a detailed schedule for the establishment of the radar composite map | US $5000 | TCTF | PatcharaPetvirojchai (TMD) Masashi Kunitsugu (JMA) Derek Leong (TCS) |
| KRA1 KRA2 KRA4 / SG4a | 8 | QPE/QPF for UFRM | - To collaborate with TC Fellowship scheme to provide QPE/QPF training to TC Members participating in the UFRM pilot projects upon a request - To provide follow-on technical assistance to MMD and PAGASA on the adaptation of HKO’s SWIRLS - Upon availability of budget, QPE/QPF workshop to be hosted by MMD | WGH WGDRR TRCG | (a) 2nd -4th (b) 1st-2nd | RSMC Tokyo HKO, CMA | (a) & (b) Conduct of training and subsequent evaluation of the training | US$5,000 | TCTF | Masashi Kunitsugu (JMA) ST Chan (HKO) |
| KRA 1 KRA 2 KRA 4 /SG4(a) | 9 | Storm surge watch scheme | - To develop the storm surge model for expansion of the region - To provide storm surge time series charts at more than one point if so requested by Members | WGH TRCG | 1st-4th | JMA | Submission of the progress report | / | / | Masashi Kunitsugu (JMA) |
| KRA 1 KRA 2 KRA 6 /SG 6b and 6c | 10 | Transfer of the Technology of the Typhoon Analysis and Prediction System (TAPS) | - To construct data server for operating the TAPS - To upgrade the user-compatible version of the TAPS - To train the typhoon forecasters on the use of the TAPS upon Member’s request | TRCG | (a) 2nd –3rd (b) 2nd –4th (c) 2nd –4th | KMA Members | Submission of the progress report | US $3,000 | TCTF | Jiyoung Kim (KMA) |

Working Group on Meteorology (WGM) – Perennial Operating Projects (POPs)

| SP’s KRA and SG | Objective Number | Objective | Action | Other WG’s involved | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Coordinator |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 1 KRA 2 KRA 4 /SG4(a) | 1 | Improvement of QPE/QPF and storm surge techniques for TC Members | (a) To collaborate with TRCG to conduct the yearly RSMC Tokyo Attachment Training for operational forecaster from TC Members including the training of storm surge model and QPE/QPF. | TRCG | 1st -4th | JMA, WMO | Submission of the evaluation report | / | / | Masashi Kunitsugu (JMA) |
| KRA 6 / SG 6b and SG 6c | 2 | Web-based typhoon forum | - To run routinely - Opening for scientists and operational forecasters upon Member’s request (nominated by Members) | WGs | 1st -4th | CMA Members | Submission of the progress report | / | / | Li qingqing (CMA) |
| KRA 1 - 6 | 3 | Tropical Cyclone Research and Review | - To publish the journal quarterly in 2013 - Improvement of the editorial procedure (includes inviting the visiting editor) - Application of online ISSN | AWG, WGs | 1st -4th | CMA, TCS Members | Progress report | US$3,000 | TCTF | Ms. Wang Dongliang & Zhou Xiao (CMA) |

Working Group on Meteorology (WGM) –Preliminary Projects (PPs)

| SP’s KRA and SG | Objective Number | Objective | Action | Other WG’s involved | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Coordinator |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 1 KRA 2 KRA 4 | 1 | Assessment report on the impact of climate change on tropical cyclone in TC region | - To carry out the preliminary studies, on the impact of climate change on tropical cyclone, especially on the unusual behavior of tropical cyclone in the TC region - To prepare the AOP for drafting the 3rd assessment report upon the results of the preliminary studies (it’ll be issued before IPCC AR6 in 2016) | WGH WGDRR TRCG | 1st – 4th | HKO/China, CMA, USA, JMA, KMA, Macao/China (coordinator) Members | Submission of the progress report | / | / | Tam Lu Man (Macao/China) |
| KRA 1 KRA 2 KRA 4 /SG4(a) | 2 | Harmonization of Tropical cyclone intensity analysis | Based on the recommendation of the best track consolidation meeting, continue to study the methodology to compare the best track datasets with the consideration on the progress of digitization of CI numbers in hard copy | / | 1st – 4th | JMA, CMA, HKO | Submission of the progress report | / | / | Masashi Kunitsugu (JMA) |
| KRA 1 KRA 2 KRA 4 /SG4(a) | 3 | Harmonization of timing of upgrade of TD to TS by various warning centers | To continue with the work of the Taskforce on TC Intensity Analysis for Upgrading TD | / | 1st – 4th | Taskforce on TC Intensity Analysis for Upgrading TD | Submission of the progress report | / | / | ST Chan (HKO) |

WORKING GROUP on HYDROLOGY (WGH) - AOP 2013

| SP's KRA and SG | Objective Number | Objective | Action | Other WGs Involved | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 6b KRA 6 SG 6b | 1 | Assessment System of Flood Control Measures on Socio-economic Impacts | To develop the manual of ASFCM system and distribute to the TC members who want to apply the system |  | coordination | (a) First (b) Second (c) Third (d) Fourth |  | (a,b,c) To develop the system manual to help members’ application of ASFCM in their own basins. (b,c,d) To consult the effect of the proposed flood control measures in selected basins | TCTF $2,000 for developing the manual | MLTM TCTF |
| KRA1 KRA 4 SG 4a SG 4bKRA5 SG 5a KRA 6 SG 6b | 2 | Extreme flood forecasting system | To develop the TC homepage for WGH members and investigate flood forecasting systems in the selected members |  | See above | - First - Second - Third - Fourth | RID of Thailand, PAGASA of Philippines Laos | (a,b) Development of the Korean and English version of TC homepage for WGH members (a,b) Development of the member’s reports and data sharing page (b,c) Investigation of the current flood forecasting systems and operation conditions in the selected basins (b,c,d) Comparison of the flood forecasting systems of the selected members | TCTF $3,000 for the investigation | MLTM TCTF |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 6 SG 6b | 3 | Project on estimation for socio-economic impact of sediment-related disaster | to improve former projects with establish common collecting format and methods of investigation for disasters to estimate estimation for socio-economic impact of sediment-related disaster and to share common technical background in TC members. | WGDRR | See above | (a)First (b)Second (c)Third (d)Fourth |  | (a) Providing a draft format to collect the record of sediment-related disaster (b) Deciding the format to collect the record of sediment-related disaster (c) To report the results of survey based on the format by each TC members (d1) To make a “Sediment-related Disaster Record Database” to share the records in TC members (d2) To report and share the results of estimation of socio-economic impact |  | NILIM SABO |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 6 SG 6b | 4 | Development of Operational System forUrban Flood Forecasting and Inundation Mapping (OSUFFIM) | todevelop a prototype real time OSUFFIM for TC Members to promote the capacity of early warning of urban flood and emergency response, particularly urban flood forecasting and inundation mapping. |  | diver | (a)First (b)Second (c)Third (d)Fourth | SMG, Macao; Sun Yat-Sen University of China; TMD/RID of Thailand | (a1) kick-off meeting for discussion plan (a2) Survey of Pilot City—Hat Yai; (b1) Data collection, analysis and procession of the chosen pilot cities (Hat Yai) (b-c) developing system (d) report the progress at IWS | TCTF $6000 for supporting activities related to OSUFFIM development | STDF of Macao; SYS Univ. ; TMD/ RID of Thailand; TCTF |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 6 SG 6b | 5 | Extend application of Xin’anjiang Model in Selected River Basins in TC Members | To promote the Capacity of Flood Forecasting for TC Members;Use the Model in Pilot River basin in Malaysia in 2013 |  | Coordination | (a)First (b)Second (c)Third (d)Fourth | BOH and Hohai University of China; DID of Malaysia | (a1) perfecting the English version of Model (China) (a2) select river basin and prepare necessary data by DID (b) Send profs/experts to Malaysia for training (c) Use the model on trial in flood season (d) report to TC IWS and Session | TCTF $2000 to support experts for training course in Malaysia | BOH of China; DID of Malaysia |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 6 SG 6b | 6 | Guidelines for extreme flood risk management in TC region | To define the concept of extreme flood and host a workshop to develop the consensus about the guideline among the members |  | See above | (a) First (b) Second (c) Third (d) Fourth |  | (a) Development of the definition of extreme flood in TC region (b,c) preparedness of WGH meeting(workshop) for TC members to discuss about TC AOP including extreme flood risk management (c)host 2nd WGH Working meeting (b,c,d) Development of consensus about the contents in the guideline among the members | TCTF $2,000 for hosting the WGH meeting( workshop) | MLTM TCTF |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a KRA 5 SG 5a KRA 6 SG 6b | 7 | Study on Prediction of Debris flow and Shallow landslide by the Satellite Rainfall Data | To study on prediction of debris flow and shallow landslide by the satellite rainfall data | WGDRR | See above | (a)First (b)Second (c)Third (d)Fourth | accept application | (b) kick-off meeting for discussion plan (c) accept proposal as pilot basin (d) Study on pilot basin |  | ICHARM |
| KRA 1 SG 1 KRA 2 SG 2 KRA 4 SG 4a, SG 5a KRA 5 SG 5a SG 5b KRA 6 SG6b | 8 | Project of Synergized Standard Operating Procedures for Coastal Multi-hazard Early Warning System (SSOP) | To develop a Manual/Handbook of Synergized Standard Operating Procedures for Coastal Multi-hazard Early Warning Systems | WGM WGDRR TRCG | Coordination Focal Point | (a)First (b)Second (c)Third (d)Fourth | PTC, ESCAP, WMO, ADRC, IOC of UNESCO | (a) Workshop of SSOP (b) Piloting in selected countries (c-d) Drafting the Manual/Handbook of SSOP |  | ESCAP funding |

SG1:  To enhance cooperation among TC Members to reduce the number of deaths by typhoon-related disasters by half in the ten years of 2006 – 2015 (using the ten years of 1990 - 1999 as the base line).

SG2:  To reduce the socio-economic impacts of typhoon-related disasters per GDP per capita by 20 per cent in the ten years of 2006- 2015 (using the ten years of 1990 - 1999 as the base line).

SG 3a:  To identify and explore the beneficial use of resources such as rainfall brought by typhoon.

SG 3b:  To study and promote the increasing use of typhoon-related beneficial effects among the Members.

SG 4a:  To provide reliable typhoon-related disaster information for effective decision making in risk management in various sectors.

SG 4b:  To strengthen capacity of the Members in typhoon-related disaster risk management in various sectors.

SG 4c:  To enhance international and regional cooperation and assistance in the field of disaster risk reduction.

SG 5a:  To promote and enhance culture of community-based disaster risk management among the Members.

SG 5b:  To promote education, training and public awareness of typhoon-related disasters among the Members.

SG 6a:  To facilitate RSMC capability to respond to the needs of the Members in forecasting and capacity building.

SG 6b:  To improve capacity of Members to provide timely and accurate user-oriented and friendly tropical cyclone products and information.

SG 6c:  To enhance capacity of Members' typhoon-related observation, monitoring, forecasting and warning.

SG 7a:  To strengthen the capacity of Typhoon Committee to effectively discharge its responsibilities and functions described in this Strategic Plan and completed its stated mission     in accordance with the Typhoon Committee’s Statute.

SG 7b:  To mobilize available resources and engage collaborators for the implementation of the strategic goals.

KRA 1:  Reduced Loss of Life from Typhoon-related Disasters.

KRA 2:  Minimized Typhoon-related Social and Economic Impacts.

KRA 3:  Enhanced beneficial typhoon-related effects for the betterment of quality of life.

KRA 4:  Improved Typhoon-related Disaster Risk Management in Various Sectors.

KRA 5:  Strengthened Resilience of Communities to Typhoon-related Disaster.

KRA 6:  Improved capacity to generate and provide accurate, timely and understandable information on typhoon-related threats.

KRA 7:  Enhanced Typhoon Committee’s Effectiveness, Efficiency and International Collaboration.

WORKING GROUP on DISASTER RISK REDUCTION (WGDRR) - AOP 2013

| SPs KRA and SGs | Objective Number | Objective | Action | Other WG’s | TCS Responsibility | Expected Quarter Completed | Other Organizations Involved | Success Indicators | Funding Required | Funding Sources | Completed Yes or No |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KRA 4 KRA 5 SG 4b SG 4c | 1 | Extending the WGTCIDS | (i) Collect disaster information from TC Members (ii) Upgrade the search option for similar Typhoon in WGTCDIS | TCS | (i) Provide guideline to support $1000 for collecting disaster information (ii) Assist in collecting disaster information from Members | Fourth | NDMI | (i) Complete collecting disaster information from Thailand, Philippines, USA and Cambodia (ii) Present various search option for finding similar Typhoon in WGTCDIS | US $4,000 | NDMI, Korea and TCTF |  |
| KRA 4 KRA 5 SG 4b SG 4c SG 5b | 2 | Provide the training program | (i) Perform Expert Mission for training disaster prevention technologies and policies including WGTCDIS | TCS | Assist in planning and performing the expert mission | Fourth | NDMI | (i) Send expert team to four members of Lao PDR, Thailand, USA, and Viet Nam | US $ 7,000 | NDMI, Korea and TCTF |  |
| KRA ALL SG ALL | 3 | Promote the international cooperation research | (i) Dispatch the experts of Korea and TCS for visiting Philippines to install the Flash Flood Alert System (FFAS) and AWS | WGH TCS | Assist in planning and performing the international cooperation research | Fourth | NDMI PAGASA | (i) Complete report on Northern Mindanao project |  | NDMI, Korea |  |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 4 | Application of SWIdget to Member countries | (i) Promote and extend the dissemination of warnings and alerts by Members through SWIC (Severe Weather Information Center) | - | Assist in liaising with focal points | Ongoing | WMO HKO | (i) Number of Members providing and using the warnings/alerts disseminated through SWIdget |  |  |  |
| KRA 4 SG 4b SG 4c KRA 5 SG 5b | 5 | Setting up of community weather stations for raising public awareness on climate changes and extreme weather | (i) Liaise with Members on requirements and ways to take part in the project (ii) Offer an expert of Hong Kong, China for visiting Viet Nam and DPR Korea to implement the community weather stations | - | Assist in liaising with focal points ad provide logistic support for the expert visits | Fourth | HKO | (i) Weather stations installed in two interested TC member | US $6,000 | TCTF |  |
| KRA4 KRA5 KRA7 SG4b SG5a SG6b | 6 | Provide benefit evaluation of Typhoon disaster prevention and preparedness | (i) survey and evaluate the response of government, department, company and person to typhoon disaster (ii) survey and evaluate the benefit of different response |  | Assist in planning and performing the international cooperation research | Fourth | CMA and tentatively KMA Macao, China Hong Kong, China | Complete collecting response of government and departments, evaluation report finalized | From TCTF: US $2,000 | CMA and TCTF |  |
| KRA ALL SG ALL | 7 | Support the Synergized Standard Operation Procedure (SSOP) project |  | WGM WGH TCS |  |  |  |  |  |  |  |

SG1:  To enhance cooperation among TC Members to reduce the number of deaths by typhoon-related disasters by half in the ten years of 2006 – 2015 (using the ten years of 1990 –

1999 as the base line).

SG2:  To reduce the socio-economic impacts of typhoon-related disasters per GDP per capita by 20 per cent in the ten years of 2006- 2015 (using the ten years of 1990 - 1999 as the

base line).

SG 3a:  To identify and explore the beneficial use of resources such as rainfall brought by typhoon.

SG 3b:  To study and promote the increasing use of typhoon-related beneficial effects among the Members.

SG 4a:  To provide reliable typhoon-related disaster information for effective decision making in risk management in various sectors.

SG 4b:  To strengthen capacity of the Members in typhoon-related disaster risk management in various sectors.

SG 4c:  To enhance international and regional cooperation and assistance in the field of disaster risk reduction.

SG 5a:  To promote and enhance culture of community-based disaster risk management among the Members.

SG 5b:  To promote education, training and public awareness of typhoon-related disasters among the Members.

SG 6a:  To facilitate RSMC capability to respond to the needs of the Members in forecasting and capacity building.

SG 6b:  To improve capacity of Members to provide timely and accurate user-oriented and friendly tropical cyclone products and information.

SG 6c:  To enhance capacity of Members' typhoon-related observation, monitoring, forecasting and warning.

SG 7a:  To strengthen the capacity of Typhoon Committee to effectively discharge its responsibilities and functions described in this Strategic Plan and completed its stated mission     in accordance with the Typhoon Committee’s Statute.

SG 7b:  To mobilize available resources and engage collaborators for the implementation of the strategic goals.

KRA 1:  Reduced Loss of Life from Typhoon-related Disasters.

KRA 2:  Minimized Typhoon-related Social and Economic Impacts.

KRA 3:  Enhanced beneficial typhoon-related effects for the betterment of quality of life.

KRA 4:  Improved Typhoon-related Disaster Risk Management in Various Sectors.

KRA 5:  Strengthened Resilience of Communities to Typhoon-related Disaster.

KRA 6:  Improved capacity to generate and provide accurate, timely and understandable information on typhoon-related threats.

KRA 7:  Enhanced Typhoon Committee’s Effectiveness, Efficiency and International Collaboration.