APPENDIX XX

Progress Report on the Fourth Assessment Report on Climate Change in 2025

Submitted by TC-AR4 Expert Team

- Following the decision of TC 57th Session, under the supervision of WGM, TC-AR4 Expert Team made remarkable progress in 2025

- On the basis of the nominations from Members, the Expert Team for TC-AR4 was composed of the following members.

- Dr. Xin HUANG (Shanghai Typhoon Institute, CMA), Coordinator, member

- Ms. Seong Hee WON (Korea Meteorological Administration), member

- Dr. Munehiko YAMAGUCHI (Japan Meteorological Administration), member

- Dr. Yin-lam NG (Hong Kong Observatory), member

- Following the structure of previous assessment reports, TC-AR4 Expert Team agreed on the draft chapters as follows:

- Chapter 1: Introduction

- Chapter 2: Observed TC activity and characteristics changes

- Chapter 3: Detection and attribution of TC changes

- Chapter 4: Tropical cyclone impacts in the Typhoon Committee region

- Chapter 5: Future Projections

- Chapter 6: Uncertainties

- Chapter 7: Recommendations for Future Work

- Chapter 8: References

- Based on expertise of the members, TC-AR4 Expert Team shared the workload and proposed the following timelines:

- Dec. 2025 (end on Mar. 2026), Collect related papers/reports and impact information of tropical cyclones on TC regions from Members.

- Jul. 2026, Complete report draft, Expert Team will hold a face-to-face meeting.

- Sep. 2026, Refine details of the assessment report.

- Nov. 2026, Submit the first draft to TCS before the 21st IWS to collect Members’ comments.

- Dec. 2026, Discussion of the first draft of report at the 21st IWS, make revision based on Members’ comments.

- Jan./Feb. 2027, Finalize the report and submit to TCS before the 59th Session, prepare for the related scientific papers.

- Mar. 2027, Submit related scientific papers to TCRR.

- With a view to offering scientific advice for the Expert Team, based on the discussion in AWG, the Expert Team invited chair of working groups to nominate several Advisors to support the preparation of the report. The following advisors were nominated by WGM and TRCG:

WGM: Dr. Wei ZHANG (Utah State University)

TRCG: Dr. Tsz Cheung LEE (Hong Kong Observatory) and Prof. Johnny Chan (Asia-Pacific Typhoon Collaborative Research Center).

- To gather available information from each Member on the possible changes in the impacts of tropical cyclones in the TC region, survey forms of the TC-AR4 were sent to directors and focal points of WGM in December 2025.

# Conclusions of TC-AR4 Expert TEAM

- TC-AR4 Expert Team agreed on the following conclusions:

- The first draft of TC-AR4 will be submitted to TCS before the 21st IWS for comments from TC Members, and the first draft will be discussed at the 21st IWS.

- Following a thorough revision process incorporating comments from TC Members, the final draft will be submitted to TCS prior to the 59th Session in 2027.

- With a view to offering scientific advice for the Expert Team, Dr. Wei ZHANG (Utah State University), Dr. Tsz Cheung LEE (Hong Kong Observatory) and Prof. Johnny Chan (Asia-Pacific Typhoon Collaborative Research Center) are nominated as advisors to support the preparation of the report.