APPENDIX XXI

Proposed Activities and Budget Framework

60th Anniversary of the ESCAP/WMO Typhoon Committee (TC60)

## 1. Background and Rationale

The year 2028 marks the 60th Anniversary of the ESCAP/WMO Typhoon Committee (TC), commemorating six decades of sustained regional cooperation in tropical cyclone monitoring, forecasting, disaster risk reduction, and capacity development across the Asia-Pacific region.

TC60 provides a timely opportunity to acknowledge this collective legacy while reaffirming the Committee’s forward-looking commitment to strengthening regional resilience, particularly in support of the Early Warnings for All (EW4All) initiative.

## 2. Purpose and Objectives

The proposed TC60 commemoration aims to:

- Recognise and commemorate 60 years of regional cooperation under the Typhoon Committee framework;

- Reinforce a shared sense of identity, ownership, and partnership among Members;

- Highlight the Committee’s continuing contribution to Early Warnings for All and regional resilience;

- Ensure cost-effectiveness, simplicity, and practicality in the design and implementation of anniversary activities.

## 3. Proposed Organisational Approach and Rundown

### 3.1 Establishment of TC60 Task Team

To ensure coordinated and efficient implementation, it is proposed to establish time-bound TC60 Task Team, using the experience of the TC50 anniversary.

TC60 Session Task Team (led by AWG Chair, with team members from TCS, ESCAP and WMO Secretariats, host Country of TC60, and others as nominated by Members, if any)

To oversee, plan and coordinate the preparation and organization of the TC60 Session and associated celebration activities, including the high-level thematic forum on Day 1 of TC60 Session.

### 3.2 TC60 Anniversary Identity

To mark the anniversary, it is proposed to develop a TC60 Anniversary logo, building on the experience of TC50 while adopting a lighter and more efficient approach.

Indicative elements include:

- Development of a TC60 anniversary logo, with Members engagement through adaptations or inputs;

- Endorsement of the final TC60 logo at TC59 in Singapore;

- Use of the TC60 identity across relevant meetings, publications, and communication materials during the one-year anniversary period;

- Adoption of a short anniversary tagline (e.g. “60 Years of International Cooperation and Regional Resilience”).

(samples)

### 3.3 TC60 Practical Souvenirs and Legacy Items

In line with the operational spirit of TC60, the following modest and practical items may be considered:

#### (a) TC60 “Early Warning Kit” [TBD]

A small, practical preparedness-themed item aligned with EW4All, for example:

- TC60-branded waterproof phone pouch or compact emergency item;

- Simple packaging highlighting TC60 and EW4All messaging.

#### (b) TC60 Legacy Photobook

- Slim photo book covering the past 10 years (building on TC50 experience);

- Key milestones presented in 10-year intervals;

- EW4All commitment page;

- Closing page: “Looking Ahead to TC70”.

#### (c) TC60 Commemorative Token

- UN-style metal challenge coin;

- Front: TC60 logo;

- Back: “ESCAP/WMO Typhoon Committee – 60 Years”.

(sample)

#### (d) TC60 Notebook and Pen

- Premium notebook for Member use during meetings;

- Minimal design with embossed TC60 logo and EW4All reference.

(sample)

### 3.4 TC60 Digital Time Capsule

To encourage Members participation with minimal administrative burden, a TC60 Digital Time Capsule may be established, with a particular focus on high-level perspectives.

Proposed approach:

- Each Member’s Permanent Representative (PR) or Head of Delegation is invited to submit one short high-level contribution reflecting on the value, impact, or future direction of the Typhoon Committee;

- Contributions may take the form of a brief written message, a short statement, or a single photo or visual element, in line with agreed guidance;

- Each submission to be clearly marked: “TC60 Digital Time Capsule – To be opened at TC70”;

- All materials to be compiled and securely archived digitally by the Typhoon Committee Secretariat (TCS) as part of the TC60 legacy record.

## 4. During TC60 Anniversary Sessions and Forums

### 4.1. TRCG Forum

It is proposed to organise a TRCG Forum in conjunction with the TC60 anniversary, as previous on the TC50, and aiming to provide a forward-looking platform that complements the commemorative activities.

Indicative focus:

- Translating TC’s 60-year legacy into future-oriented research, operational collaboration, and innovation;

- Strengthening linkages between research, operations, and policy under EW4All;

- Highlighting the role of younger scientists and next-generation experts in sustaining TC’s mission.

### 4.2. TC60 Commemorative Segment

A dedicated 60-minute TC60 Commemorative Moment may be integrated into the Session programme:

- 6-10 speakers (experts and former key contributors to Typhoon Committee activities), with 10 minutes per speaker, each representing one decade (1966–2026);

- Brief reflections highlighting key lessons learned, institutional continuity, and future directions of the Typhoon Committee;

- A concluding group photograph, symbolising a collective commitment to the Early Warnings for All initiative.

## 5. Indicative Budget Framework

Consistent with the approach adopted for TC50 (a total special budget of 80,000USD), it is proposed to apply a similar overall budget envelope for TC60 activities.

### 5.1 TRCG Forum Budget

- USD 30,000

To support:

- Organisation of the TRCG Forum in conjunction with TC60;

- Limited logistical, documentation, and coordination costs;

- Participation support in line with established TC practices (inviting experts)

### 5.2 TC60 Coordination and Activities Budget (TCS)

- USD 50,000

To support:

- Overall coordination and organisation of TC60 activities by TCS;

- Development of TC60 identity and communication materials;

- Production of souvenirs and legacy items;

## 6. Indicative Timeframe for TC60 Activities

| Phase | Period | Key Activities |
| --- | --- | --- |
| Pre-Phase: Conceptual Preparation Phase | 2026 | • Initial internal reflections and ideas by TCS on the scope, scale, and guiding principles of TC60;• Review of experiences and lessons learned from TC50 and other milestone anniversaries;• Preliminary identification of possible activities, legacy elements, and linkages with EW4All;• Informal consultations with selected Members, Working Group Chairs, and TRCG on feasible options |
| Phase 0: Endorsement Phase | TC59 Session (February 2027) | • Submission of the TC60 proposed activities and budget framework to TC59 for consideration and approval;• Endorsement of the overall TC60 commemoration framework, including Task Teams, TRCG Forum, and indicative budget envelopes;• Guidance from Members on scope, priorities, and implementation approach. |
| Phase 1: Preparatory Phase | Post-TC59 – Q3 2027 | • Establishment of TC60 Task Teams following TC59 approval and confirmation of scope and deliverables;• Initial concept development for TC60 identity, souvenirs, legacy items, and digital time capsule;• Preliminary coordination with TRCG on the organisation of the TRCG Forum in conjunction with TC60. |
| Phase 2: Design and Coordination Phase | Q4 2027 – Q1 2028 | • Development and finalisation of the TC60 anniversary logo and tagline;• Preparation of TC60 communication and visibility materials;• Issuance of invitations and guidance to Permanent Representatives (PRs) for high-level contributions to the TC60 Digital Time Capsule;• Substantive planning and agenda development for the TRCG Forum, TRCG experts invitations; Roll-out of TC60 identity across meetings, publications, and official communications; |
| Phase 3: Implementation Phase | Q1 2028 (TC60 Year; TC Session in February 2028) | TC60 SESSION/TRCG FORUM |
| Phase 4: Consolidation and Legacy Phase | Post-Session 2028 | • Finalisation and secure archiving of TC60 legacy materials by TCS;• Documentation of TC60 activities and outcomes for institutional record;• Preparation of selected materials for preservation and future opening at TC70. |

## 7. Budget estimate

Consistent with the approach adopted for TC50 (a total special budget of 50,000USD), for TC60 only.

| Item | Description | DSA for 5 days in Thailand | No. of Days | TOTAL per person | Estimated No. of Lecturers | Sub-Total in USD | Grand Total in USD |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Per diem for 6-10 lecturers of TC60 | 180 | 5 | 900 | 10 | 9,000 |  |
|  | Air Ticket for 6-10 lecturers of TC60 |  |  |  | 10 | 17,000 |  |
| 1 | Total Lecturers cost for TC50 |  |  |  |  |  | 26,000 |
| 2 | Rental of Venue (USD3000 per day) |  | 4 |  |  | 12,000 |  |
| 3 | Rental of Projector (USD550 per day) |  | 4 |  |  | 2,200 |  |
| 4 | Gifts |  |  |  |  | 9,800 | 24,000 |
| Total Estimation |  |  |  |  |  |  | 50,000 |